GYEITI WORKPLAN FOR 2025/2026

In keeping with the discussions at the 83rd MSG, the Workplan was circulated to all members for feedback by November 30,2025.   No feedback was received. A reminder was subsequently dispatched. Unfortunately, no response was received.

Notwithstanding the foregoing, the Workplan is now submitted to the MSG for its engagement with its constituency / stakeholders to obtain the necessary buy-in.  Upon completion of this exercise, a formal report on the engagement is to be submitted to the Secretariat for its record.

The Secretariat appreciates if the engagements can be completed on or before December 31, 2025.

| No / Priority | EITI Requirement |  | Output / Deliverables | Task/Activity |  | Performance Indicator | Start | End | Amount GYD | Funding Source |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | EITI Compliance |  | Production and publication of the EITI Reports in line with the EITI Standard (i) FY 2023 -Dec 2025 (December 31, 2025) (ii) FY 24 Dec 26 (iii) FY 25 – Dec 26 | Procure an Independent Administrator to produce the 7th h EITI report (ii) Procure an independent administrator for FY 24 and FY 25 Reports (April 2025) |  | MSG approval of TORs Approved TOR for IA for FY 24 and FY 25 . MSG approval of reports and Publication within obligatory deadline of December 31 the (i) 7th EITI reports (FY 23) (ii) 8th EITI Report (FY 24) (iii) 9th EITI report (FY 25) | September 2025 | December 2026 | 26,000,000 | World Bank |  |
| 1.1 | EITI Requirement 2.5 |  | Develop a BO Register linked to the Deeds & Commercial Registry | - Interface with Deeds & Commercial Registry - Develop and implement the Open Ownership (OO) software linked to Deeds & Commercial Registry - Collect ownership data from companies and verify its accuracy before entry into the register |  | Beneficial Ownership Register with EI sector data. | Janruary 2026 | June 2026 2026 | 15,000,000 | GOG |  |
| 1.2 | EITI Compliance/Systematic Disclosure |  | Mainstreaming Contextual Data | Identify 3 GOG entities for initial Mainstreaming support |  | Contextual data identified or mainstreamed by agency/ministry | June 2025 | June 2026 | 159,000 | GOG |  |
| 1.3 | Validation |  | Completed Validation Templates (Stakeholder Engagement, Outcomes and Impact, and Transparency) | Source information and accurately complete all validation templates |  | Acceptance and approval of templates by MSG and submission to the EITI International Secretariat | September 2025 | December 2025 | 100.000 | GOG |  |
| 1.4 | MSG Governance and Oversight |  | MSG Capacity Building (In house and External ) | Workshop on EITI Standard, Roles, and Responsibilities of MSG members |  | Orientation of (New) MSG Members | September 2025 | December 2025 | N/A |  |  |
| 1.5 | EITI Requirement 1 |  | National Secretariat Capacity Building | Staff-specific capacity development based on institutional assessment |  | Enhanced productivity and support to the MSG Number of training programs conducted and participation rates | October 2024 | September 2025 | N/A | World Bank |  |
| 1.6 | EITI Requirement 1.2.5 / Anti-Corruption |  | Publication of Anti-corruption Policy by reporting companies and SOEs | Develop and share sample anti-corruption policies with reporting companies. Announcements, publication in dailies, formal letters to reporting companies, and MSG representatives support publishing anti-corruption policies. |  | Year-end count/percentage who published anti-corruption policy statements | April 2025 | December 2025 | N/A |  | N/A |
| 1.7 | EITI Requirement 2.4 / Public Access to Contracts and Licenses |  | Enable public access to contracts and licenses in key sectors | Work with GOG agencies and industry to develop a disclosure roadmap and contract/license database |  | Number of contracts/licenses publicly disclosed, Database created | July 2025 | June 2026 | N/A |  | N/A |
| 1.8 |  |  | GOG Policy on Contract Disclosure | GYEITI engages MNR to develop it Contract Disclosure Policy and make it publicly available |  | An approved and publicly accessible Contract Disclosure Policy | July 2025 | September 2025 | N/A |  | N/A |
| 1.9 |  |  | Public access to all EIAs | MRN / EPA to compile a list of all EIAs for the EIT sector and determine a list of missing EIAs |  | All EIAs for the EI sector are publicly available | July 2025 | December 2025. | N/A |  | N/A |
| 1.10 |  |  | Assessment of the impact of ASM and how to integrate it into EITI disclosures | Field assessment and data collection on ASM |  | Findings and recommendations on integrating ASM into EITI disclosures | September 2025 | December 2025 |  |  |  |
| 2.0 | EITI Requirement 2.4 / Public access to contracts and licenses |  | Public access to all contracts and concession agreements in the oil & gas, mining, forest, and agriculture (fisheries) sectors | Identify, liaise, and convene with custodial GOG agencies of contracts & licenses. Convene meetings with industry to explain EITI requirements for disclosure. |  | Develop and implement a roadmap for public access to contracts & licenses, inclusive of the contract/license database. | July 2025 | December 2025 | N/A | GOG |  |
| 2.1 | EITI Requirement 1.3 / Civil Society Engagement |  | Civil Society Organizations’ (CSOs’) capacity for effective advocacy of EITI impact evaluation strengthened. | Build CSOs’ capacity to understand the 2023 EITI standards |  | Number of capacity building workshops held; attendance logs and reports from workshops held | July 2025 | June 2026 | N/A (Virtual) | N/A |  |
| 2.2 | EITI Requirement 1.5 / Broader constituency’s inputs incorporated in MSG decisions |  | MSG Constituency Feedback | MSG engagements with a broader constituency |  | Documentation/ Report on consultative engagements | July 2025 | June 2026 | N/A | N/A |  |
| 2.3 | EITI Requirements 4.1, 7.1 / Public access to EITI disclosures |  | Identify Legal Barriers to the Regulatory Framework in the Sector | Develop Policy Paper; Parliamentary review of confidentiality in the Tax Act. |  | Roadmap to address legal barriers EITI disclosures | January 2025 | June 2025 | 3,000,000 | GOG |  |
| 2.4 | EITI Requirement 6.2 / Enhanced EITI disclosures on SOEs |  | Strengthen Disclosures from State-Owned Enterprises | Virtual Workshop on the rules and practices of the financial relationship b/w GOG and SOEs |  | Report on SOEs and GOS relations to be published on the GYEITI website | October 2025 | June 2026 | N/A | N/A |  |
| 2.5 | EITI Requirement 2.1/ Legal Framework and Fiscal Regime |  | To Enhance the public understanding of how energy transition policies affect the extractive sectors | •Locate and Share information on government plans, commitments, and subsidies for energy transition on the Website •Host a seminar or Webinar forum to discuss energy transition policies •Collect and analyze feedback from awareness initiatives to gauge understanding and address concerns |  | Greater public awareness of Energy transition policies and its implications on the Extractive Sector Number of information shared Attendance rate Survey results showing an increase in awareness of energy transition | April 2026 | June 2026 | N/A | N/A |  |
| 2.6 | EITI Requirement 2.2/ Contracts and Licenses Allocation |  | To Promote transparent and gender-equitable processes in the allocation of contracts and licenses Greater access for women-led businesses and fairer, more transparent allocations | • Locate and Identify the Government’s Policy on gender equality and equity • Examine the guidelines and processes used to award contracts • Host workshops to engage women-led businesses in bidding. |  | • Number of relevant policies found • Number of Male and Female Contracts awarded - Percentage of applications fro - m women-led businesses. Number of gender-inclusive sessions held. | July 2025 | June 2026 | N/A | N/A |  |
| 2.7 | EITI Requirement 4.9 |  | GGB to submit royalty data to GGMC using taxpayer identification number (TIN) | Support GGB and GGMC on use of License Number as a unique identifier as a substitute for TINS |  | GGB and GGMC use of TIN for EITI reporting | Q3 2025 | Q4 2025 | N/A | N/A |  |
| 2.8 | EITI Requirement 2.6/State Participation |  | Enhance systematic disclosure of information on state ownership, SOEs, etc NICIL’s website of information available of MoF website | - Identify GOG Policy - Engage NICIL and agencies for data sharing Incorporate data into report |  | Public reports on state ownership, SOEs, and financial data. | July 2025 | December 2025 | N/A | N/A |  |
| 2.9 | EITI Requirement / Validation |  | Capacity Building for Journalists | Workshop for local journalists on the EITI |  | Increased and accurate coverage of GYEITI reports and activities - Organize 1 workshops - 100% Attendance rate - 100% of participants report improved coverage skills - Percent rise in GYEITI-related media coverage - Number of Attendees expressing satisfaction with the workshop | July 2025 | October 2025 | 100,000 | GYD |  |
| 2.10 |  |  | Public access to all MSG Minutes from Sept 2021 | Publish all Minutes on the GYEITI website since 2021 Validation |  | All MSG Minutes are publicly available | July 2025 | October 2025 | N/A | GOG |  |
| 3.0 - | EITI Requirement 7 / Public Awareness |  | Dissemination of the 6th and 7th EITI Reports. Annual Progress. Reports to strengthen awareness around population centers nationwide. Make available Plain language report at expos, conferences, schools clubs etc. constituency consultations etc. | Prepare summarized and simplified reports for public understanding and awareness. EITI Reports will be widely distributed at outreach sessions in key government entities, administrative regions and key stakeholders inclusive of educational institutions |  | Printed reports available for distribution (Plain language version) | January 2026 | June 2026 | 2,000,000 | GOG |  |
| 3.1 |  |  |  |  |  | The number of outreach sessions convened, and the number of participants benefitted from them. The number of reports distributed to the public. | October 2025 | June 2026 | 5,730,000 | GOG |  |
| 3.2 | EITI Requirement 7 / Enhanced public awareness of GYEITI activities |  | Pullup Banners | Develop messages for banners Recruit vendors and produce banners for public display |  | Increased awareness using banners | October 2025 | June 2026 | 200,000 | GOG |  |
| 3.3 | EITI Requirement 7 / Enhanced public awareness of GYEITI activities |  | Digital Billboards | Produce GYEITI messages and procure vendors to display messages in digital formats. |  | Increased awareness of GYEITI and the country’s EI transparency | September 2025 | March 2026 | 1,440,000 | GOG |  |
| 3.4 | EITI Requirement 7 / Enhanced public awareness of GYEITI activities |  | Increase digital, social media, and other awareness | Produce/procure jingles and infomercials, radio and television interviews, etc; schools/universities outreach |  | Target audience and number of /frequency of sessions. | July 2025 | March 2026 | 2,240.000 | GOG |  |
| Color Scheme |  | Interpretation |  |  |
|  |  | Priority 1 – disclosure practice or activity required by the EITI Standard. |  |  |
|  |  | Priority 2 – disclosure practice or activity expected by the EITI Standard. |  |  |
|  |  | Priority 3 – disclosure practice or activity encouraged by the EITI Standard. |  |  |
|  |  | Priority 4 – disclosure practice or activity beyond the scope of the EITI Standard |  |  |