## workplan 2025-26
[5 empty] | 2025 | [11 empty] | 2026
Task | Activity | Start date | End Date | Duration (days) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
1 | Production and publication of the 7th (FY 2023) and 8th EITI Report | 2025-09-01 | 2025-12-01 | 91 | bar: 2026 Jun to 2026 Dec
1.1 | Develop a BO Register linked to the Deeds & Commercial Registry | 2026-01-01 | 2026-06-01 | 151 | bar: 2026 Jan to 2026 Jun
1.2 | Mainstreaming Contextual Data | 2025-06-01 | 2026-06-01 | 365 | bar: 2025 Jun to 2025 Aug; 2026 Jan to 2026 Jun
1.3 | Completed Validation Templates (Stakeholder Engagement, Outcomes and Impact, and Transparency) | 2025-09-01 | 2025-12-01 | 91
1.4 | MSG Capacity Building | 2025-09-01 | 2025-12-01 | 91
1.5 | National Secretariat Capacity Building | 2025-09-01 | 2025-10-01 | 30 | bar: 2025 Aug
1.6 | Publication of Anti-corruption Policy by reporting companies and SOEs | 2025-04-01 | 2025-12-01 | 244 | bar: 2025 Apr to 2025 Aug
1.7 | Enable public access to contracts and licenses in key sectors | 2025-07-01 | 2026-06-01 | 335 | bar: 2025 Jul to 2025 Aug; 2026 Jan to 2026 Jun
1.8 | GOG Policy on Contract Disclosure | 2025-07-01 | 2025-09-01 | 62 | bar: 2025 Jul to 2025 Aug
1.9 | Public access to all EIAs | 2025-07-01 | 2026-06-01 | 335 | bar: 2025 Jul to 2025 Aug; 2026 Jan to 2026 Jun
1.1 | Assessment of the impact of ASM and how to integrate it into EITI disclosures | 2025-09-01 | 2025-12-01 | 91
2 | Public access to all contracts and concession agreements in the oil & gas, mining, forest, and agriculture (fisheries) sectors | 2025-07-01 | 2025-12-01 | 153 | bar: 2025 Jul to 2025 Aug
2.1 | Civil Society Organizations’ (CSOs’) capacity for effective advocacy of EITI impact evaluation strengthened. | 2025-07-01 | 2026-06-01 | 335 | bar: 2025 Jul to 2025 Aug; 2026 Jan to 2026 Jun
2.2 | MSG Constituency Feedback | 2025-07-01 | 2026-06-01 | 335 | bar: 2025 Jul to 2025 Aug; 2026 Jan to 2026 Jul
2.3 |  | 2025-01-01 | 2025-06-01 | 151 | bar: 2025 Jan to 2025 Aug; 2026 Jan to 2026 Jun
2.4 | Strengthen Disclosures from State-Owned Enterprises | 2025-10-01 | 2026-06-01 | 243 | bar: 2026 Jan to 2026 Jun
2.5 | To Enhance the public understanding of how energy transition policies affect the extractive sectors | 2025-04-01 | 2026-06-01 | 426 | bar: 2026 Jan to 2026 Jun
2.6 | To Promote transparent and gender-equitable processes in the allocation of contracts and licenses and allow for greater access for women led businesses for fairer more transparent allocations | 2025-07-01 | 2026-06-01 | 335 | bar: 2025 Apr to 2025 Aug; 2026 Jan to 2026 Jul
2.7 | GGB to submit royalty data to GGMC using taxpayer identification number (TIN) | 2025-07-01 | 2025-12-01 | 153 | bar: 2025 Jun to 2025 Aug; 2026 Jan
2.8 | Enhance systematic disclosure of information on state ownership, SOEs, etc and on NICIL's website and MOF website | 2025-07-01 | 2025-12-01 | 153 | bar: 2025 Jun to 2025 Aug; 2026 Jan
2.9 | Capacity Building for Journalists | 2025-07-01 | 2025-10-01 | 92 | bar: 2025 Jul to 2025 Aug; 2026 Jan
2.1 | Public access to all MSG Minutes from Sept 2021 | 2025-07-01 | 2025-10-01 | 92 | bar: 2025 Jul to 2025 Aug
3 | Dissemination of the 6th and 7th EITI Reports and 2022/23 and 2024 Annual Progress Reports to strengthen awareness around population centers nationwide. | 2026-01-01 | 2026-06-01 | 151 | bar: 2026 Jan to 2026 Jun
3.1 |  | 2025-10-01 | 2026-06-01 | 243 | bar: 2026 Jan to 2026 Jun
3.2 | Pullup Banners | 2025-10-01 | 2026-06-01 | 243 | bar: 2026 Jan to 2026 Jun
3.3 | Digital Billboards | 2025-09-01 | 2026-03-01 | 181 | bar: 2026 Jan to 2026 Mar
3.4 | Increase digital, social media, and other awareness | 2025-07-01 | 2026-03-01 | 243 | bar: 2025 Jul to 2025 Aug; 2026 Jan to 2026 Mar