GYEITI

WORKPLAN 2025 TO 2026

| No / Priority | EITI Requirement | Output / Deliverables | Task/Activity | Performance Indicator | Start | End | Amount GYD | Funding Source |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | EITI Compliance | Production and publication of the 7th (FY 2023) EITI Report in line with the Standard | Procure an Independent Administrator to produce the 7th h EITI report | MSG acceptance, approval, and publication of the 7th EITI report | September 2025 | December 2025 | 26,000,000 | World Bank |  |
| 1.1 | EITI Requirement 2.5 | Develop a BO Register linked to the Deeds & Commercial Registry | - Interface with Deeds & Commercial Registry - Develop and implement the Open Ownership (OO) software linked to Deeds & Commercial Registry - Collect ownership data from companies and verify its accuracy before entry into the register | Beneficial Ownership Register with EI sector data. | Janruary 2026 | June 2026 2026 | 15,000,000 | GOG |  |
| 1.2 | EITI Compliance/Systematic Disclosure | Mainstreaming Contextual Data | Identify 3 GOG entities for initial Mainstreaming support | Contextual data identified or mainstreamed by agency/ministry | June 2025 | June 2026 | 159,000 | GOG |  |
| 1.3 | Validation | Completed Validation Templates (Stakeholder Engagement, Outcomes and Impact, and Transparency) | Source information and accurately complete all validation templates | Acceptance and approval of templates by MSG and submission to the EITI International Secretariat | September 2025 | December 2025 | 100.000 | GOG |  |
| 1.4 | MSG Governance and Oversight | MSG Capacity Building | Workshop on EITI Standard, Roles, and Responsibilities of MSG members | Orientation of (New) MSG Members | September 2025 | December 2025 | N/A |  |  |
| 1.5 | EITI Requirement 1 | National Secretariat Capacity Building | Staff-specific capacity development based on institutional assessment | Enhanced productivity and support to the MSG Number of training programs conducted and participation rates | October 2024 | September 2025 | N/A | World Bank |  |
| 1.6 | EITI Requirement 1.2.5 / Anti-Corruption | Publication of Anti-corruption Policy by reporting companies and SOEs | Develop and share sample anti-corruption policies with reporting companies. Announcements, publication in dailies, formal letters to reporting companies, and MSG representatives support publishing anti-corruption policies. | Year-end count/percentage who published anti-corruption policy statements | April 2025 | December 2025 | N/A |  | N/A |
| 1.7 | EITI Requirement 2.4 / Public Access to Contracts and Licenses | Enable public access to contracts and licenses in key sectors | Work with GOG agencies and industry to develop a disclosure roadmap and contract/license database | Number of contracts/licenses publicly disclosed, Database created | July 2025 | June 2026 | N/A |  | N/A |
| 1.8 |  | GOG Policy on Contract Disclosure | GYEITI engages MNR to develop it Contract Disclosure Policy and make it publicly available | An approved and publicly accessible Contract Disclosure Policy | July 2025 | September 2025 | N/A |  | N/A |
| 1.9 |  | Public access to all EIAs | MRN / EPA to compile a list of all EIAs for the EIT sector and determine a list of missing EIAs | All EIAs for the EI sector are publicly available | July 2025 | December 2025. | N/A |  | N/A |
| 1.10 |  | Assessment of the impact of ASM and how to integrate it into EITI disclosures | Field assessment and data collection on ASM | Findings and recommendations on integrating ASM into EITI disclosures | September 2025 | December 2025 |  |  |  |
| 2.0 | EITI Requirement 2.4 / Public access to contracts and licenses | Public access to all contracts and concession agreements in the oil & gas, mining, forest, and agriculture (fisheries) sectors | Identify, liaise, and convene with custodial GOG agencies of contracts & licenses. Convene meetings with industry to explain EITI requirements for disclosure. | Develop and implement a roadmap for public access to contracts & licenses, inclusive of the contract/license database. | July 2025 | December 2025 | N/A | GOG |  |
| 2.1 | EITI Requirement 1.3 / Civil Society Engagement | Civil Society Organizations’ (CSOs’) capacity for effective advocacy of EITI impact evaluation strengthened. | Build CSOs’ capacity to understand the 2023 EITI standards | Number of capacity building workshops held; attendance logs and reports from workshops held | July 2025 | June 2026 | N/A (Virtual) | N/A |  |
| 2.2 | EITI Requirement 1.5 / Broader constituency’s inputs incorporated in MSG decisions | MSG Constituency Feedback | MSG engagements with a broader constituency | Documentation/ Report on consultative engagements | July 2025 | June 2026 | N/A | N/A |  |
| 2.3 | EITI Requirements 4.1, 7.1 / Public access to EITI disclosures | Identify Legal Barriers to the Regulatory Framework in the Sector | Develop Policy Paper; Parliamentary review of confidentiality in the Tax Act. | Roadmap to address legal barriers EITI disclosures | January 2025 | June 2025 | 3,000,000 | GOG |  |
| 2.4 | EITI Requirement 6.2 / Enhanced EITI disclosures on SOEs | Strengthen Disclosures from State-Owned Enterprises | Virtual Workshop on the rules and practices of the financial relationship b/w GOG and SOEs | Report on SOEs and GOS relations to be published on the GYEITI website | October 2025 | June 2026 | N/A | N/A |  |
| 2.5 | EITI Requirement 2.1/ Legal Framework and Fiscal Regime | To Enhance the public understanding of how energy transition policies affect the extractive sectors | •Locate and Share information on government plans, commitments, and subsidies for energy transition on the Website •Host a seminar or Webinar forum to discuss energy transition policies •Collect and analyze feedback from awareness initiatives to gauge understanding and address concerns | Greater public awareness of Energy transition policies and its implications on the Extractive Sector Number of information shared Attendance rate Survey results showing an increase in awareness of energy transition | April 2026 | June 2026 | N/A | N/A |  |
| 2.6 | EITI Requirement 2.2/ Contracts and Licenses Allocation | To Promote transparent and gender-equitable processes in the allocation of contracts and licenses Greater access for women-led businesses and fairer, more transparent allocations | • Locate and Identify the Government’s Policy on gender equality and equity • Examine the guidelines and processes used to award contracts • Host workshops to engage women-led businesses in bidding. | • Number of relevant policies found • Number of Male and Female Contracts awarded - Percentage of applications fro - m women-led businesses. Number of gender-inclusive sessions held. | July 2025 | June 2026 | N/A | N/A |  |
| 2.7 | EITI Requirement 4.9 | GGB to submit royalty data to GGMC using taxpayer identification number (TIN) | Support GGB and GGMC on use of License Number as a unique identifier as a substitute for TINS | GGB and GGMC use of TIN for EITI reporting | Q3 2025 | Q4 2025 | N/A | N/A |  |
| 2.8 | EITI Requirement 2.6/State Participation | Enhance systematic disclosure of information on state ownership, SOEs, etc NICIL’s website of information available of MoF website | - Identify GOG Policy - Engage NICIL and agencies for data sharing Incorporate data into report | Public reports on state ownership, SOEs, and financial data. | July 2025 | December 2025 | N/A | N/A |  |
| 2.9 | EITI Requirement / Validation | Capacity Building for Journalists | Workshop for local journalists on the EITI | Increased and accurate coverage of GYEITI reports and activities - Organize 1 workshops - 100% Attendance rate - 100% of participants report improved coverage skills - Percent rise in GYEITI-related media coverage - Number of Attendees expressing satisfaction with the workshop | July 2025 | October 2025 | 100,000 | GYD |  |
| 2.10 |  | Public access to all MSG Minutes from Sept 2021 | Publish all Minutes on the GYEITI website since 2021 Validation | All MSG Minutes are publicly available | July 2025 | October 2025 | N/A | GOG |  |
| 3.0 - | EITI Requirement 7 / Public Awareness | Dissemination of the 6th and 7th EITI Reports and 2022/23 and 2024 Annual Progress Reports to strengthen awareness around population centers nationwide. | Prepare summarized and simplified reports for public understanding and awareness. Reports will be widely distributed at outreach sessions in all government administrative regions. | Printed reports available for distribution (Plain language version) | January 2026 | June 2026 | 2,000,000 | GOG |  |
| 3.1 |  |  |  | The number of outreach sessions convened, and the number of participants benefitted from them. The number of reports distributed to the public. | October 2025 | June 2026 | 5,730,000 | GOG |  |
| 3.2 | EITI Requirement 7 / Enhanced public awareness of GYEITI activities | Pullup Banners | Develop messages for banners Recruit vendors and produce banners for public display | Increased awareness using banners | October 2025 | June 2026 | 200,000 | GOG |  |
| 3.3 | EITI Requirement 7 / Enhanced public awareness of GYEITI activities | Digital Billboards | Produce GYEITI messages and procure vendors to display messages in digital formats. | Increased awareness of GYEITI and the country’s EI transparency | September 2025 | March 2026 | 1,440,000 | GOG |  |
| 3.4 | EITI Requirement 7 / Enhanced public awareness of GYEITI activities | Increase digital, social media, and other awareness | Produce/procure jingles and infomercials, radio and television interviews, etc; schools/universities outreach | Target audience and number of /frequency of sessions. | July 2025 | March 2026 | 2,240.000 | GOG |  |

GYEITI Secretariat