GUYANA EXTRACTIVE INDUSTRY TRANSPARENCY  INITIATIVE (GYEITI)

ANNUAL PROGRESS REPORT FOR  2024

Guyana Extractive Industries Transparency Initiative (GYEITI) Secretariat

55 Main Street, Georgetown 
Website: Home - EITI
Social Media: Facebook: EITI Guyana

Telephone: 231 2503-5

FEBRUARY 2025

CONTENTS

Acronyms	2

Acknowledgment	3

Background and Introduction	4

Highlights of Achievements and Challenges	5

Overview of Activities and Outcomes	6

Implementation of 2024 Workplan	6

Production and Publication GYEITI  6th (FY 2022) Report	6

Stakeholders’ Consultations	7

Beneficial Ownership Roadmap	8

Mainstreaming / Systematic Disclosure Feasibility Study	9

Data Analyses	9

Communications Strategy 2021 - 2025	10

Outreach and Dissemination	10

MSG Scorecard	13

Agreed Upon Procedure	13

MSG Policy Manual	13

Open Data Policy	14

Capacity Assessment and Building	14

Secretariat Staff	14

MSG	15

2025 Workplan Preparation	15

MSG Meetings	16

Constituency Feedback Mechanism	16

Assessment of Performance against EITI Requirements	17

Strengths and Weaknesses Identified in EITI Process GYEITI	42

Total Implementation Cost	42

Expense Report	43

Details of the MSG during the Period	43

# Acronyms

| AG | Auditor General |
| --- | --- |
| APR | Annual Progress Review |
| BO | Beneficial Ownership |
| CSO | Civil Society Organization |
| EITI | Extractive Industries Transparency Initiative |
| FY | Fiscal Year |
| GDP | Gross Domestic Product |
| GoG | Government of Guyana |
| GYD | Guyanese Dollar |
| GYEITI | Guyana Extractive Industries Transparency Initiative |
| IA | Independent Administrator |
| MNR | Ministry of Natural Resources |
| MSG | Multi-Stakeholder Group |
| NPTAB | National Procurement Tender Administrative Board |
| WB | World Bank |

# Acknowledgment

The Multi-Stakeholder Group (MSG) of Guyana EITI acknowledges the support of key stakeholders involved in promoting accountability and transparency regarding Guyana's extractive resources. Our collective goal is to ensure that the resources are used to improve the lives of the country's citizens.

To this end, we would like to recognize the role of the Government of Guyana in its continued support for accountability and transparency across the resource value chain benchmarked on the EITI Standard. Further, we would like to recognize the key role played by the EITI Champion, Hon. Vickram Bharrat MP, and the Ministry of Natural Resources in providing operational and budget support for GYEITI.

We also recognize the pivotal role played by Civil Society as a key constituency that has contributed to monitoring and recommendation support along the way. Civil society's consistent and thoughtful concerns have guided our policies and disclosure practices. GYEITI outreach and dissemination efforts are strengthened because citizens know that civil society is a key part of the EITI framework.

We also recognize that for the EITI to work, industry players and the government must provide credible data for disclosures. We thank the extractive companies for providing timely and credible data supporting GYEITI disclosure efforts.

We also acknowledge the GYEITI Secretariat, whose tireless administrative and technical support in implementing the Workplan has ensured the MSG achieved the activities outlined in the Workplan.

Finally, we recognize and appreciate the citizens of Guyana for their feedback and comments on our work on transparency and accountability in the extractive sector. Our collective goal is to ensure that the resources are used to improve the lives of the country's citizens.

# Background and Introduction

Guyana joined the Extractive Industries Transparency Initiative (EITI) in 2017 to advance and promote transparency and accountability in managing oil, gas, mineral, and other natural resources. Guyana EITI (GYEITI) has published five EITI reports covering fiscal years 2017 through 2021. As a globally accepted initiative, EITI has afforded Guyana and other resource-endowed countries a unique opportunity to maximize their natural resource wealth for sustainable and equitable development.

The initial impact of EITI in Guyana has been significant, mainly through recommendations on national policy and regulatory reforms. GYEITI has achieved several initial reforms, including advocacy for contract transparency and enhanced data disaggregation in the natural resource sector, as well as improvements in export information accuracy, license allocation coordination, and efforts to enhance data accuracy and timeliness.

In addition, GYEITI is already providing important lessons to shape laws and regulations for the oil and gas sector, which only started production in 2019. For instance, GYEITI advocated and engaged stakeholders on its GYEITI Report recommendations on introducing open and transparent license award processes and contracting in the natural resource sector, particularly in oil and gas and mining. Further, GYEITI has provided recommendations through its reports to strengthen transparency, oversight, and control in the oil and gas and minerals sectors, consistent with international best practices.

Guyana earned a “Fairly Low” (52/100) score on its 2021 Validation. Fourteen actions were identified for correction. The MSG is addressing these actions aimed at improving implementation in Guyana. Under Requirement 1.5.b, implementing countries must undertake an annual review of the work plan, considering progress and challenges towards implementation. To this end, this Annual Progress Review highlights the status of GYEITI implementation during FY 2024.

The review is grouped into four components, namely: The first segment details an assessment of progress made against the GYEITI 2024 Workplan; the second highlights progress made towards implementation of EITI requirements; the third cohesively outlines strengths and weaknesses in the implementation of the EITI process during the period under review, while the fourth looks at activities implemented by the broader constituency of the Multi-stakeholder arrangement.

Finally, the Report contains information on the MSG’s composition and participation during the reporting period, as well as a summary of the implementation costs during the same period.

# Highlights of Achievements and Challenges

During FY 2024, Guyana published its FY 2022 EITI Report. The report shows an increase in contribution from the extractive sector to the economy.

Contribution to GDP:

- Total contribution increased by 50.51% (from 44.78% in 2021 to 67.4% in 2022).

- Oil/Gas contributions increased significantly by 78.28% (from 34.95% in 2021 to 62.31% in 2022).

- Mining’s share decreased sharply by 48.74% (from 8.35% in 2021 to 4.28% in 2022).

Contribution to Government Revenues:

- Total contribution increased by 59.42% (from 45.54% in 2021 to 72.6% in 2022).

- Oil/Gas revenue increased significantly by 79.43% (from 37.92% in 2021 to 68.04% in 2022).

- Mining’s fiscal contribution decreased by 40.64% (from 7.16% in 2021 to 4.25% in 2022).

Completed a systematic disclosure/mainstreaming feasibility study

- Developed an MSG Scorecard to track attendance

- GYEITI 2024 Workplan preparation and implementation

- Agreed Upon Procedure to support data quality

- MSG Policy Manual to strengthen MSG governance and oversight

- Developed GYEITI Open Data Policy

- Beneficial Ownership terms of reference and report assessment

- Institutional and Capacity Assessment

- Capacity Building for the MSG and National Secretariat

Notwithstanding these achievements, GYEITI activities faced some challenges. Some outreach and dissemination activities were stalled due to scheduling challenges of MSG members and delays in decision making. Communications activities though included in the approved workplan, needed another round of approval from the Communications Committee before implementation.  Capacity challenges continue to impact deliverables at the Secretariat. This was partly addressed in the latter part of the year with the addition of two staff. Emphasis of developing technical skills, full grasp of the EITI Standard, multistakeholder engagement skills, and EITI implementation knowledge experience should be addressed to enable the secretariat’s full support to the MSG.

# Overview of Activities and Outcomes

Below is a summary of key work activities for FY 2024.

# Implementation of 2024 Workplan

## Production and Publication GYEITI  6th (FY 2022) Report

The MSG approved the Terms of Reference (TOR) for the 6th EITI report on March 27, 2024, with a subsequent approval of BDO Guyana as Independent Administrator to produce GYEITI’s FY 2022 report. A scoping study to define materiality thresholds, entities for disclosure, and reporting templates was approved on July 26, 2024. Based on the approved scoping report, the IA commenced the process of data gathering and reconciling payments from companies and State entities.

The IA and Secretariat coordinated reporting workshops with government and industry stakeholders on July 29, 2024. At the workshop, the IA provided information on completing the reporting templates, timeliness, and sign-off requirements to ensure data credibility. Reporting entities shared their challenges regarding appropriate sign-off, the timeline for completion, and the constraints faced by staff who were also engaged in other end-of-year activities for their agencies.

Per the MSG decision, the Secretariat collected data on and supported the drafting of the contextual section of the FY 2022 report. Delays in the submission of both revenue and contextual data by reporting entities affected the timely completion of the first draft of the GYEITI 2022 report.

The MSG approved and published the FY 2022 Guyana EITI Report on December 20, 2024, in keeping with the requirements of the EITI 2023 standard.

### Stakeholders’ Consultations

In keeping with EITI Requirement 7.1, which seeks to encourage Public Debate on activities in the country’s extractive sector, a series of consultations was conducted by the MSG and the Secretariat. These consultations aimed at enhancing awareness of the GYEITI and Guyana’s EITI efforts and progress since officially becoming an EITI member.

Public engagements were limited due to staffing challenges and delays in preparing materials for MSG approval procedures, which also affected their availability to participate in some instances.  The latter half of 2024 saw limited engagements due to the staff’s and MSG members’ support in the preparation of the FY 22 EITI report.

The engagements with stakeholders are as follows:

- Government/ state entities- July 29, 2024 (am)

- Industry stakeholders- July 29, 2024 (pm)

The GYEITI Secretariat coordinated an engagement session with stakeholders from state entities on July 29, 2024. At this session, the IA shared details on correctly filling out the data submission templates for the 6th report.

- Engagement with the University of Guyana, March 12, 2024, and July 16, 2024

- Youths in Natural Resources, June 28, 2024

- Region 9, Lethem, July 29, 2024.

- Education and Awareness.

On March 12, 2024, the National Secretariat and members of the MSG engaged the University of Guyana Academic Board on EITI and transparency within the extractive sectors, highlighting the role the university could play in engagement and shaping of opinions.

- Youths in Natural Resources

On June 28, 2024, the Youths in Natural Resources were presented with an insight into the EITI and the GYEITI. The interactive discussion focused not only on Transparency but also on the role of the EITI and the effort that Guyana is making to implement the global standard.

- University of Guyana Student Engagement Session July 16, 2024

The National Secretariat and members of the MSG organized an Engagement Session, which discussed the rationale behind EITI and its role in prudently managing the extractive resources. It spoke of Guyana’s progress over the years, and the challenges and opportunities encountered along the path to EITI implementation.

- Lethem Stakeholders Engagement

A more broad-based dialogue with Region 9, approved by the MSG, and one of the activities aimed at promoting dialogue among stakeholders, was cancelled due to scheduling difficulties with MSG members and the Region 9 Administration. The activity is now slated to be completed under the 2025 work plan.

# Beneficial Ownership Roadmap

The GYEITI MSG approved the Beneficial Ownership Roadmap in July 2018. This roadmap outlines the steps and actions GYEITI must take to ensure compliance with EITI requirements 2.5. Procurement challenges, including failures of bids to meet the requirements set out in the tender, delayed the recruitment of a consultancy to implement the roadmap. In late 2023, the MSG revised and approved the Terms of Reference (ToR) to recruit a Beneficial Ownership consultant. The bid was opened to local and foreign consultants.

In early March 2024, the BO consultancy was awarded to a team comprising Diane Barker, Michael Barron and Tim Law. The consultant engaged with various stakeholders in government, industry, and civil society, international partners, and interfaced with the Secretariat and the MNR in the execution of the consultancy.

On March 27, 2024, the Multistakeholder Group of the Guyana Extractive Industries Transparency Initiative (GYEITI) completed its review and approved the Inception Report for the implementation of the Beneficial Ownership Road Map.

The MSG approved the consultant’s final report in August 2024. It includes harmonizing the threshold and definitions for disclosure between the EITI requirements and Guyana laws. and a BO register with pertinent information on beneficial owners of extractive companies.

The 2025 Work Plan will begin to systematically address recommendations outlined in the roadmap, such as working with the Deeds and Commercial Regulatory Agency (DCRA) on capacity building, data collection, and reporting.

# Mainstreaming / Systematic Disclosure Feasibility Study

The MSG reviewed and approved the terms of Reference (ToR) for the World Bank Consultant to conduct a feasibility study on mainstreaming EITI disclosures in Guyana. The study, which was completed in May 2024, was approved by the MSG on July 10, 2924.

The feasibility study identified key barriers and gaps to the routine disclosure of EITI data, including comprehensiveness, disaggregation, quality and assurance, format, accessibility, and frequency.  The assessment for Guyana indicates that less than 50% of information is routinely disclosed in the mining, forestry, and fishing sectors. In comparison, the oil and gas sector routinely discloses greater than 50% of EITI information.

The implementation of the study's recommendations will pave the way for mainstreaming in Guyana in accordance with the EITI Standard 2023.

# Data Analyses

In keeping with the requirement for data accessibility and to improve public awareness of and access to extractive data, a comparative analysis covering revenues and expenditures for FY 2017 to FY 2020 was completed by the Secretariat. This information is presented in an open data format and structure, making it accessible and comprehensible to the average person.

A data bulletin for the FY 2021 report was completed. These analyses were prepared from the information in the published EITI reports. The EITI reports and analyses –Data Bulletin- can be accessed at: DATA DISSEMINATION BULLETIN: FISCAL YEAR 2020/2021 - EITI

GYEITI Website

The GYEITI was redesigned and launched in late 2023. Throughout 2024, the   Secretariat, working alongside IT consultant Mr. Roger Gajraj, completed the migration of all historical and pertinent documents from its old webpage. These documents include work plans, reports, strategies, and newsletters in formats that allow for ease of access and use. The webpage is evolving and constantly assessed for its relevance in terms of format and content.

The GYEITI Webpage is one of the significant communication modalities for engaging its stakeholders and disseminating information.  The Guyana EITI webpage, which can be accessed at https://eiti.gy.

# Communications Strategy 2021 - 2025

The GYEITI 2021 - 2025 Communications Strategy, which the MSG approved in August 2021, laid the foundation for subsequent annual communication action plans. In 2023, the MSG approved an annual communication action plan that outlined activities GYEITI intended to execute in 2023. Some approved activities could not be completed in 2023 and hence were rolled over to 2024. Similarly, communication activities not completed in 2024 have been included in the 2025 draft Workplan. Notwithstanding the challenges, GYEITI executed the following activities in line with its Communications Strategy 2021-2021.

## Outreach and Dissemination

The Secretariat completed several outreach and dissemination activities outlined in the 2024 Workplan. These activities aim to foster debates and discussions among stakeholders and the public at large, focusing on the EITI initiatives in Guyana, the extractive sector’s contribution to economic development, and the benefits citizens can derive from the extractive sector's revenues.

- Merundoi Radio Serial Drama

GYEITI and Merundoi agreed to air radio dramas to support awareness of GYEITI activities. Merundoi is a well-established Radio drama series and has a wide reach in terms of the public and those in the Mining communities.

In December 2024, twenty-one (21) episodes were completed and began airing on NCN radio in Georgetown (Region 4), where over 50% of Guyana’s over 800k citizens reside, and satellite stations in the various administrative regions of Guyana, where the mining and extractive communities reside. An additional twenty-seven (27) will be broadcast by the end of the first quarter of 2025.

The messaging focused on promoting awareness around GYEITI activities and the EITI requirements, and how they relate to the day-to-day activities in the life of miners at their camps and mining communities.

- MSG Co-Chairs’ Video Interviews

As of December 31, 2024, the Secretariat coordinated video recordings of the three co-chairs. The recordings are being edited by Sagacity Media. Upon completion of the edits and approval by the MSG, the videos will be widely disseminated and promoted through the GYEITI website, YouTube, Instagram, Facebook, and other social media platforms.

- University of Guyana (UG) Engagement

Academic Board Engagement

On March 12, 2024, the Communications and Outreach Committee of GYEITI held discussions with the university’s Academic Board about the implementation of EITI in Guyana and the role of the university in promoting dialogue on transparency and accountability in the extractive sector. Both the Guyana EITI and the university are committed to working together on stimulating debates among the relevant stakeholders regarding transparency within the extractive sectors and how they might play their part in this process.

- Students and Lecturers' Engagement

As a result of the Academic Board’s engagement, the GYEITI MSG met with the University academic members and students from various faculties who were apprised about the implementation of EITI in Guyana, transparency in the extractive sectors, and the EITI requirements. The event was held on Tuesday, July 16, 2024, at the Education Lecture Theatre, Turkeyen Campus.

Guyana’s EITI National Coordinator, Dr. Prem Misir, gave a brief overview of what EITI is, how it originated, and why it was important for countries such as Guyana to implement its principles.

His presentation highlighted the benefits of EITI implementation for countries like Guyana, emphasizing the need for effective implementation, particularly in light of Guyana's poor score in its first validation in 2021. Following the presentations, there was a vibrant question-and-answer session, which yielded several interventions from both the student body and faculty.  Three (3) Members of the MSG were in attendance and took part in the engagement session. The total number of attendees at the event exceeded 45 persons.

- Region 9 RDC, Mayor and Chamber Engagement

On July 29, 2024, the Secretariat had an engagement session with stakeholders from Lethem, Region 9, at the RDC office during which Guyana’s EITI implementation was discussed. The small gathering of ten, comprising senior Regional Administration officers and private sector business, discussed the EITI Standard, its requirements, and some of the milestones Guyana has achieved along the path to EITI implementation. Copies of the FY 2020 and 2021 Reports were shared with 9 participants at the meeting, and the findings and conclusions were presented and discussed.

Discussions were also held on convening a broader-based engagement in Lethem towards the end of 2024. This event was not convened due to scheduling and availability of MSG members and local officials.

- Youths in Natural Resources

On June 28, 2024, the GYEITI engaged youths in natural resources drawn from the Ministry of Natural Resources Youths in Natural Resources Apprenticeship Programme for 2024 aimed at fostering appreciation and career ambition around the natural resources sector.

Twenty-five (25) youths participated. The interactive discussion focused not only on Transparency but also on the role of the EITI and the effort that Guyana is making to implement the global standard.

- EITI Newsletter

Two Newsletters were produced during 2024. The January-March 2024 Newsletter was published in April 2024, and the April-November 2024 Newsletter was published in January 2025.

- Joseph O. F. Haynes Schools Debating Competition

The JOF Haynes Schools Debating Competition is a premier debating competition among secondary schools in Guyana.  The competition, which is organized by the Ministry of Education, was identified as an appropriate mode to engage the youth in understanding the GYEITI activities and the principles of the EITI. The collaboration with the Ministry of Education is aimed at:  enhancing the students' understanding and appreciation of Guyana's extractive sectors and how they can contribute to its prudent management of the sector; challenge students to explore the interplay between transparency, economic development, and sustainability within Guyana’s context, while also considering the role of EITI in the extractive industry and encourage critical thinking among youths around the economic, environmental, and ethical dimensions of the extractive industry, making them suitable for high school debates.

The Secretariat submitted relevant topics to the organizers of the Competition. The Debate was shifted from the last school term in 2024 due to scheduling difficulties. The competition was shifted to the first quarter of 2025.

Notwithstanding these achievements, delays in decision-making at the MSG level adversely affected the delivery of some communication activities.  Comprehensive preparation of materials for scrutiny, timely approvals at the Communications Committee and MSG levels, and scheduling should be strengthened to ensure effective and timely execution of communications activities.

# MSG Scorecard

The MSG approved its Attendance Scorecard at the 71st Statutory Meeting held on January 17, 2024. The Scorecard replaced a format for recording MSG members’ attendance at statutory and special meetings and guides monitoring attendance to guide implementation of the provisions as set out in the MSG Terms of Reference. It is a one-page traffic-light summary that assigns an average score for each member and constituency for attendance at MSG meetings.  The MSG agreed to socialize this document internally over a period, following which it would become a public document.

# Agreed Upon Procedure

To ensure quality assurance of data submitted by government entities for EITI disclosures, the MSG, through the Ministry of Natural Resources, executed an Agreed Upon Procedure (AUP) with the Auditor General of Guyana. The AUP defined an interim set of guidelines that the AG would follow to sign off on reporting templates submitted by government entities. The 2021 EITIT Validation findings on Guyana highlighted deficiencies in data quality.

# MSG Policy Manual

The MSG Terms of Reference which was adopted in September 2020 was revised and replaced with the MSG Policy Manual to address gaps and strengthen governance and oversight of the Multi-Stakeholder Group. Key revisions or additions include the Code of Conduct, the addition of No Objection and Modified Consensus to the Decision-Making Protocol, amongst others.

The 75th Meeting of the Multi-Stakeholders Group on May 15, 2024, approved the adoption of the MSG Policy Manual. The Manual was made public at the EITI’s website at: https://eiti.gy/multi-stakeholder-group/

# Open Data Policy

Per EITI Requirement 7.2, implementing countries may agree on a clear, open data policy on the access, release, and reuse of EITI data. Subsequently, the MSG developed and adopted the GYEITI Open Data Policy in May 2024.  GYEITI Open Data Policy is published on the GYEITI website and can be accessed at: http://eiti.gy

# Capacity Assessment and Building

## Secretariat Staff

The World Bank Consultant, Mr. Sam Tokpah, undertook an assessment of the capacity of the staff of the GYEITI Secretariat.  The assessment identified gaps in staff skills vis-à-vis core competencies defined in the staff’s job requirements. The assessment also benchmarked the MSG’s expectations of the Secretariat against productivity and support rendered to the MSG. To address these gaps, several one-on-one knowledge transfer engagements were undertaken with staff members. For example, the consultant and the Administrator teamed up to draft the workplan; support the Communications Officer on new stories/newsletters and other communications support, as well as support to the Admin Assistant on updating the MSG Scorecard.  Group trainings centered on key provisions of the EITI 2023 Standard.

Additional capacity building efforts, based on the 2024 assessment, will be implemented in 2025, including computer skills, report writing and analysis, budgeting, and deeper insights on EITI implementation.

The Secretariat also participated in four (4) EITI International Webinars along with the MSG on new provisions of the EITI requirement.

The Communications Officer attended a virtual workshop on Energy Transition held in September 2024 facilitated by Climate Tracker-a Caribbean NGO.

## MSG

Following approval of the Policy Manual, the MSG agreed to a new members’ orientation for those who joined the MSG in the latter part of 2023. Accordingly, three new members from the industry, civic, and industry, along with personnel from the Secretariat, participated in a virtual orientation exercise on May 30, 2024. Consultant Sam Tokpah facilitated this engagement.

The MSG also participated in five (5) virtual training engagements offered by the EITI International Secretariat to the Latin American Countries implementing the EITI. The training covered topics on the new provisions.

On March 14, 2024, members of GYEITI MSG joined other oversight boards in the Latin America and the Caribbean region for a webinar with the EITI International Secretariat.  This event introduced the new requirements of the EITI 2023 Standard, outlining how countries in the region should implement them. Given that the 2023 EITI Standard is the only standard in force, all reports published in 2024 must be compliant with it. The presentation briefly presented the new provisions in the EITI Standard. 
The MSG also participated in other capacity-building events as described below:

- Beneficial Ownership Session, May 9, 2024

- Environmental Disclosure session, June 6, 2024

- Energy Transition Session, August 8, 2024.

- Webinar on Public Engagements, on September 12, 2024

# 2025 Workplan Preparation

In the latter months of 2024, the Secretariat commenced drafting the 2025 Workplan to continue the implementation of the corrective measures stemming from the 2021 validation and assessment of gaps in the 2021 and 2022 GYEITI Reports.

Several challenges experienced during 2024 resulted in planned activities not being implemented, especially around communications and outreach activities. Recommendations emanating from the Beneficial Ownership Road Map and Systematic Disclosure Feasibility Study, as well as those from the 2022 GYEITI Report, have been captured in the workplan.

The 2025 Workplan will also be dedicated to the GYEITI preparation for Guyana’s Second Validation scheduled for October 2025.

# MSG Meetings

The MSG held nine (9) statutory monthly meetings and ten (10) special sessions in 2024. The special sessions address specific matters that require urgent attention, mainly matters relating to the FY 2022 EITI report for Guyana.  Meetings attendances were recorded.

There were four active committees during 2024, namely Communications and Outreach, Workplan, Validation, and Term of Reference, Independent Administrator and Report, and CO-Chairs Committee. A fourth committee, Legal and Regulatory, was formed in the latter part of the year, but no engagement. The other committees were active and held regular or as-needed meetings to guide the Secretariat with workplan implementation, drafting policies, coordinating stakeholder engagements, and other technical issues that require in-depth discussion and scrutiny. The Committees also provided advisory support to the MSG as defined by the responsibilities outlined in the MSG Policy Manual.   The Capacity Building Committee remained inactive in 2024. The Co-Chairs of the MSG met regularly in preparation of statutory meetings and as deemed necessary. Reports/feedback were presented to MSG at its statutory meetings.

In keeping with the MSG Policy Manual, the Champion of Guyana EITI is required to attend at least one meeting of the MSG with rights of voice but no vote. Consequently, the Minister of Natural Resources, Hon. Vickram Bharrat, attended an in-person meeting of the MSG on xxx, 2024. He acknowledged the work of the MSG in implementing the principles of the EITI in Guyana and commended them for their efforts in publishing the 2020 EITI Report for Guyana and the lifting of the EITI Board’s suspension on the country.

# Constituency Feedback Mechanism

Each constituency represented on the MSG is mandated to seek feedback from its broader membership to ensure that the work activities and other decisions involving implementation reflect the constituency and not the individual member. Section 5.3.3 of the TOR states members must “be able to liaise on behalf of GYEITI with their constituency to, among other things, disseminate GYEITI results and receive feedback.”

Industry

Representatives from the industry caucus separately in two primary blocks: oil and gas and mining. Representatives from the oil sector meet to discuss EITI matters and their impact on operations. The mining sector does the same. As such, their input to GYEITI activities reflects the views from their constituencies, which may differ between the two groups.

Government

Government representatives on the MSG regularly seek input through WhatsApp and phone calls on issues pertinent to MSG decisions and operations. This practice continued in 2024 and covered the government’s input on the work plan.

Civil Society

Civil society members regularly caucus as a constituency, forming the basis for their input in GYEITI matters. Each caucus engagement is documented. While civil society members are selected as individuals, they represent certain segments of the civic space. Individual members also seek feedback from the civic space they represent on the MSG.

# Assessment of Performance against EITI Requirements

| Requirement | Progress |
| --- | --- |
| 1.1 Government engagement. Requirement 1.1(a) The government is required to issue an unequivocal public statement of its intention to implement the EITI. The head must make the statement of state or government or an appropriately delegated government representative. Requirement 1.1(b) The government is required to appoint a senior individual to lead the implementation of the EITI. The appointee should have the confidence of all stakeholders, the authority, and the freedom to coordinate action on the EITI across relevant ministries and agencies and mobilize resources for EITI implementation. Requirement 1.1(c) The government must be fully, actively, and effectively engaged in the EITI process. Requirement 1.1 (d) The government must ensure that senior government officials are represented in the multi-stakeholder group. | Minister of Natural Resources and EITI Champion, the Honorable Vickram Bharrat, MP, attended the 71st MSG meeting on January 17, 2024. At the meeting, the minister underscored Government’s unwavering commitment to the EITI process and to transparency in governance. He expressed his confidence in the MSG in implementing the EITI Standard and the corrective measures coming out of the 2021 Validation. Government’s representation on the MSG comprised Senior officials. There are four primary members and four alternates that serve on the MSG and in the Committees of the MSG. The government is represented on the MSG through the Ministry of Finance, Ministry of Natural Resources, Office of the Prime Minister, Guyana Revenue Authority, The government’s annual attendance score average score was 1.5 (Sept 2023-May 2024) |
| Details from score card 1.2 Company engagement. Requirement 1.2 (a) Companies must be fully, actively, and effectively engaged in the EITI process. Requirement 1.2 (b) The government must ensure an enabling environment for company participation concerning relevant laws, regulations, administrative rules, and actual practice in implementing the EITI. The fundamental rights of company representatives substantively engaged in the EITI, including but not restricted to multi-stakeholder group members, must be respected. Requirement 1.2 (c) The government must ensure no obstacles to company participation in the EITI process. | Industry / companies representation is drawn mainly from extractive companies active in the sector. This constituency is active in MSG matters, with an annual average attendance score of 1.4 for the period Sept 2023 to May 2024. During the period under review, the sector’s participation was well documented through the minutes of the meetings. Like government and civil society representation, industry has four seats as primary members and four seats in the capacity of alternates at the table, representing the critical sectors of petroleum, mining, and forestry. Representation is drawn from senior executives and senior-level managers. |
| 1.3 Civil Society Engagement Requirement 1.3 (a) Civil society must be fully, actively, and effectively engaged in the EITI process. Requirement 1.3 (b) The government must ensure an enabling environment for civil society participation concerning relevant laws, regulations, administrative rules, and actual practice in implementing the EITI. The fundamental rights of civil society substantively engaged in the EITI, including but not restricted to members of the multi-stakeholder group, must be respected. Requirement 1.3 (c) The government must ensure no obstacles to civil society participation in the EITI process. Requirement 1.3 (d) The government must refrain from actions that narrow or restrict public debate concerning implementing the EITI. Requirement 1.3 (e) Stakeholders, including but not limited to multi-stakeholder group members, must: I. Be able to speak freely on transparency and natural resource governance issues. ii. Be substantially engaged in the design, implementation, monitoring, and evaluation of the EITI process, and ensure that it contributes to public debate. iii. Have the right to communicate and cooperate. iv. Be able to freely express opinions about the EITI without restraint, coercion, or reprisal. | Civil Society participation is a critical and integral component of the MSG and the decision-making process. Civil Society representation is needed to form a quorum at each meeting of the MSG and the Committees. Its contribution in all aspects of the MSG's work, including the rotation-based chairmanship, enables meaningful participation in decision-making. . There is an enabling environment for civil society participation in the EITI. Civil society is entirely, actively, and effectively engaged in designing, implementing, monitoring, and evaluating the EITI process. Civil Society is very active and participates in outreach efforts to promote public debate, protest actions against industry for noncompliance as it relates to safeguarding the environment, and on matters that affect the citizens of Guyana. There were no instances or occurrences where the government restricted or posed obstacles to civil society in 2023. Members openly and freely discuss matters on the extractive sector, and beyond. Average attendance score for civil society was 1.9 for the period September 2023 to May 2024. |
| Requirement (1.4) Multi-stakeholder group. a) The government must commit to working with civil society and companies and establish a multi-stakeholder group to oversee the implementation of the EITI. In establishing the multi-stakeholder group, the government must: I. Ensure that the invitation to participate in the group is open and transparent. ii. Ensure that stakeholders are adequately represented. This does not mean that they need to be equally represented numerically. The multi-stakeholder group must comprise appropriate stakeholders, including but not necessarily limited to: the private sector; civil society, including independent civil society groups and other civil society such as the media and unions; and relevant government entities, which can also include parliamentarians. Each stakeholder group must have the right to appoint its representatives, bearing in mind the desirability of pluralistic and diverse representation. The nomination process must be independent and free from any suggestion of coercion. Civil society groups involved in the EITI as multi-stakeholder group members must be operationally and, in policy terms, independent of government and/or companies. iii. Consider establishing the legal basis of the group. b) The multi-stakeholder group must agree to clear public Terms of Reference (ToR’s) for its work. The ToRs should, at a minimum, include provisions on: The role, responsibilities, and rights of the multi-stakeholder group: i. Members of the multi-stakeholder group should have the capacity to carry out their duties. ii. The multi-stakeholder group should undertake effective outreach activities with civil society groups and companies, including through media, websites, and letters, informing stakeholders of the government’s commitment to implementing the EITI and the central role of companies and civil society. The multi-stakeholder group should also widely disseminate public information from the EITI process, such as the EITI Report. iii. Members of the multi-stakeholder group should liaise with their constituency groups. Approval of work plans, EITI Reports, and annual activity reports: iv. The multi-stakeholder group is required to approve annual work plans, the appointment of the Independent Administrator, the Terms of Reference for the Independent Administrator, EITI Reports, and the yearly activity report. v. The multi-stakeholder group should oversee the EITI reporting process and engage in Validation. Internal governance rules and procedures: vi. The EITI requires an inclusive decision-making process throughout implementation, with each constituency being treated as a partner. Any member of the multi-stakeholder group has the right to table an issue for discussion. The multi-stakeholder group should agree and publish its procedures for nominating and changing multi-stakeholder group representatives, decision-making, the duration of the mandate, and the frequency of meetings. This should include ensuring that there is a process for changing group members that respect the principles set out in Requirement (1.4.a.) The MSG has per diems for attending EITI meetings or other payments to MSG members; this practice should be transparent and not create conflicts of interest. vii. There should be sufficient advance notice of meetings and timely circulation of documents before their debate and proposed adoption. viii. The multi-stakeholder group must keep written records of its discussions and decisions. | The MSG was constituted in September 2021 for a period of three years. Except for resignations, members continued serving on the MSG during 2024. There were 4 resignations of civil society members (Dian Khan; Larry Carryl, Gomin Comacho and Nicholas Fredericks) in 2022 and one Industry member resignation (Mathias Niewenhous-,) in September 2023. The industry replacement was done in October 2023, while the four vacant civil society positions were filled in November 2023. The MSG was active and robust in 2024. Each constituency was equally represented and had equal rights on the MSG. The life of the current MSG came to an end on November 25 2024 on completion of the FY 22 EITI Report No per diems or honorarium were requested, extended to, or accepted by MSG members in 2024. The members of the MSG provide voluntary service. However, members of the MSG from remote communities that are inaccessible receive full reimbursement for logistical expenses to participate in the Meetings. As far as practicable, sufficient advance notice and circulation of documents are given. MINUTES and records are kept for each meeting of the MSG. |
| Requirement 1.5 Work plan. The multi-stakeholder group is required to maintain a current work plan, fully costed and aligned with the reporting and Validation deadlines established by the EITI Board. The work plan must: a) Set EITI implementation objectives linked to the EITI Principles and reflect national priorities for the extractive industries. Multi-stakeholder groups are encouraged to explore innovative approaches to extending EITI implementation to increase the comprehensiveness of EITI reporting and public understanding of revenues and promote high standards of transparency and accountability in public life, government operations, and business. b) Reflect the results of consultations with key stakeholders and be endorsed by the multi-stakeholder group. c) Include measurable and time-bound activities to achieve the agreed objectives. The scope of EITI implementation should be tailored to contribute to the objectives identified during the consultation process. The work plan must: i. Assess and outline plans to address potential capacity constraints in government agencies, companies, and civil society that may hinder effective EITI implementation. ii. Address the scope of EITI reporting, including plans for addressing technical reporting aspects, such as comprehensiveness and data reliability (Requirements 4.1 and 4.9). iii. Identify and outline plans to address any potential legal or regulatory obstacles to EITI implementation, including, if applicable, any plans to incorporate the EITI Requirements within national legislation or regulation. iv. Outline the multi-stakeholder group’s plans for implementing Validation and EITI reporting recommendations. d) Identify domestic and external funding sources and technical assistance where appropriate to ensure timely implementation of the agreed work plan. e) Be made widely available to the public, for example, published on the national EITI website and/or other relevant ministry and agency websites, in print media, or in places that are easily accessible to the public. f) Be reviewed and updated annually. In reviewing the work plan, the multi-stakeholder group should consider extending the detail and scope of EITI reporting, including addressing issues such as revenue management and expenditure (5.3), transportation payments (4.4), discretionary social expenses (6.1.b), ad-hoc sub-national transfers (5.2.b), beneficial ownership (2.5) and contracts (2.4). Under Requirement 1.4.b (viii), the multi-stakeholder group must document its discussions and decisions. g) Include a timetable for implementation aligned with the reporting and Validation deadlines established by the EITI Board (see provision 8), which considers administrative requirements such as procurement processes and funding. | The Secretariat developed the 2025 work plan during the latter months of 2024. This work plan includes several deliverables rolled over from the previous 2023-2024 workplan. Due to several challenges internal and external to the MSG, these work plan activities could not be completed within the stimulated timeline. The new work plan will be receiving input from the MG constituents before being approved, The 2025 work plan addresses inter alia, the following: - Open Data - Beneficial Ownership - Systematic Disclosure - Contract Transparency - Licenses Register - Anti-Corruption - Environment - Gender - Data Quality and Assurance - Energy Transition - Public Engagement and Debate - Preparation of the FY 2023 report - Preparing submissions for the 2025 Validation The 2025 work plan is expected to be tailored towards meeting the EITI Standard 2023 requirements and addressing the deficiencies pointed out in the 2021 Validation through the continued implementation of a raft of corrective measures in addition to recommendations from previous EITI reports. The work plan is expected to be funded primarily by the Government of Guyana through the budget of the Ministry of Natural Resources. Following its approval, the 2025 work plan will be posted on the Guyana EITI website. |
| Requirement 2: Legal and institutional framework, including allocating contracts and licenses. Requirement 2.1 Legal framework and fiscal regime. a) Implementing countries must disclose a description of the legal framework and fiscal regime governing the extractive industries. This information must include a summary description of the fiscal regime, including the level of fiscal devolution, an overview of the relevant laws and regulations, and information on the roles and responsibilities of the appropriate government agencies. b) Where the government is undertaking reforms, the multi-stakeholder group is encouraged to document such reforms Requirement (2.2) License allocations. a) Implementing countries are required to disclose the following information related to the award or transfer of licenses about the companies covered in the EITI Report during the accounting period covered by the EITI Report: i., a description of the process for transferring or awarding the license; ii. the technical and financial criteria used; iii. information about the recipient(s) of the license that has been transferred or awarded, including consortium members where applicable; and iv. any non-trivial deviations from the applicable legal and regulatory framework governing license transfers and awards. It is required that the information set out above is disclosed for all license awards and transfers during the accounting year covered by the EITI Report, including license allocations about companies that are not included in the EITI Report, i.e., where their payments fall below the agreed materiality threshold. Any significant legal or practical barriers preventing such comprehensive disclosure should be documented and explained in the EITI Report, including an account of government plans for overcoming such barriers and the anticipated timescale for achieving them. b) Where companies covered in the EITI Report hold licenses allocated before the accounting period of the EITI Report, implementing countries are encouraged, if feasible, to disclose the information set out in 2.2(a) for these licenses. c) Where licenses are awarded through a bidding process during the accounting period covered by the EITI Report, the government is required to disclose the list of applicants and the bid criteria. d) Where the requisite information set out in 2.2(a-c) is already publicly available, including a reference or link in the EITI Report is sufficient. e) The multi-stakeholder group may wish to include additional information on the allocation of licenses in the EITI Report, including commentary on the efficiency and effectiveness of licensing procedures. Requirement (2.3) Register of licenses. a) The term license in this context refers to any license, lease, title, permit contract or concession by which the government confers on a company(ies) or individual(s) rights to explore or exploit oil, gas, and/or mineral resources. b) Implementing countries are required to maintain a publicly available register or cadastral system(s) with the following timely and comprehensive information regarding each of the licenses about companies covered in the EITI Report: i. License holder(s). ii. Where collated, coordinates of the license area. Where coordinates are not collated, the government must ensure that the license area's size and location are disclosed in the license register and that the coordinates are publicly available from the relevant government agency without unreasonable fees and restrictions. The EITI Report should include guidance on accessing the coordinates and the data's cost if any. The EITI Report should also document plans and timelines for making this information freely and electronically available through the license register. iii. Date of application, date of award, and duration of the license. iv. In the case of production licenses, the commodity is produced. It is expected that the license registers or cadastre includes information about licenses held by all entities, including companies and individuals or groups that are not included in the EITI Report, i.e., where their payments fall below the agreed materiality threshold. Any significant legal or practical barriers preventing such comprehensive disclosure should be documented and explained in the EITI Report, including an account of government plans for seeking to overcome such barriers and the anticipated timescale for achieving them. c) Where the information set out in 2.3.b is already publicly available, it is sufficient to include a reference or link in the EITI Report. Where such registers or cadastres do not exist or are incomplete, the EITI Report should disclose any gaps in the publicly available information and document efforts to strengthen these systems. In the interim, the EITI Report should include the information in 2.3.b above. Requirement (2.4) Contracts. a) Implementing countries are encouraged to publicly disclose any contracts and licenses that provide the terms attached to the exploitation of oil, gas, and minerals. b) It is required that the EITI Report documents the government’s policy on disclosing contracts and licenses governing oil, gas, and minerals exploration and exploitation. This should include relevant legal provisions, actual disclosure practices, and any planned or underway reforms. Where applicable, the EITI Report should provide an overview of the contracts and licenses that are publicly available and include a reference or link to the location where these are published. c) The term contract in 2.4(a) means i. The full text of any contract, concession, production-sharing agreement or other agreement is granted or entered into. The government provides the terms for exploiting oil, gas, and mineral resources. ii. The full text of any annex, appendix, or rider establishes details relevant to the exploitation rights described in 2.4(c)(i) or execution. iii. The full text of any alteration or amendment to the documents described in 2.4(c)(i) and 2.4(c)(ii). d) The term license in 2.4(a) means i. The full text of any license, lease, title, or permit by which a government confers on a company (ies) or individual(s) rights to exploit oil, gas, and/or mineral resources. ii. The full text of any annex, appendix, or rider establishes details relevant to the exploitation rights described in 2.4(d)(i) or execution. ii. The full text of any alteration or amendment to the documents described in 2.4(d)(i) and 2.4(d)(ii). Requirement (2.5) Beneficial ownership. a) It is recommended that implementing countries maintain a publicly available register of the beneficial owners of the corporate entity (ies) that bid for, operate, or invest in extractive assets, including the identity (ies) of their beneficial owner(s), the level of ownership and details about how ownership or control is exerted. Where possible, beneficial ownership information should be incorporated in existing filings by companies to corporate regulators, stock exchanges, or agencies regulating extractive industry licensing. Where this information is already publicly available, the EITI Report should include guidance on how to access this information b) It is required that i. The EITI Report documents the government’s policy and MSG’s discussion on beneficial ownership disclosure. This should include details of the relevant legal provisions, actual disclosure practices, and any planned or underway reforms related to beneficial ownership disclosure. ii. By 1 January 2017, the multi-stakeholder group publishes a roadmap for disclosing beneficial ownership information under clauses (c)-(f) below. The MSG will determine all milestones and deadlines in the roadmap, and the MSG will evaluate the implementation of the roadmap as part of the MSG’s annual activity report. c) As of 1 January 2020, it is required that implementing countries request and companies disclose beneficial ownership information for inclusion in the EITI report. This applies to a corporate entity (ies) that bid for, operate, or invest in extractive assets and should include the identity(ies) of their beneficial owner(s), the level of ownership, and details about how ownership or control is exerted. Any gaps or weaknesses in reporting on beneficial ownership information must be disclosed in the EITI Report, including naming entities that failed to submit all or parts of the beneficial ownership information. A country facing constitutional or significant practical barriers to implementing this requirement by 1 January 2020 may seek adapted implementation under requirement 8.1. d) Information about the beneficial owner's identity should include the beneficial owner's name, nationality, country of residence, and identifying any politically exposed persons. It is also recommended that the national identity number, date of birth, residential or service address, and means of contact are disclosed. e) The multi-stakeholder group should agree on an approach for participating companies assuring the accuracy of the beneficial ownership information they provide. This could include requiring companies to attest to the beneficial ownership declaration form through sign-off by a member of the senior management team or senior legal counsel or submit supporting documentation. f) Definition of beneficial ownership: i. A beneficial owner in a company means the natural person(s) who directly or indirectly ultimately owns or controls the corporate entity. ii. The multi-stakeholder group should agree on an appropriate definition of the beneficial owner. The definition should be aligned with (f)(i) above and take international norms and relevant national laws into account, and should include ownership threshold(s). The definition should also specify reporting obligations for politically exposed persons. iii. Publicly listed companies, including wholly-owned subsidiaries, are required to disclose the stock exchange name and include a link to the stock exchange filings where they are listed. iv. In the case of joint ventures, each entity within the venture should disclose its beneficial owner(s) unless it is publicly listed or is a wholly-owned subsidiary of a publicly listed company. Each entity is responsible for the accuracy of the information provided. g) The EITI Report should also disclose such companies' legal owners and share of ownership. Requirement (2.6) State participation. Where state participation in the extractive industries gives rise to material revenue payments, implementing countries must disclose: a) An explanation of the prevailing rules and practices regarding the financial relationship between the government and state-owned enterprises (SOEs), e.g., the rules and practices governing transfers of funds between the SOE(s) and the state, retained earnings, reinvestment, and third-party financing. For EITI reporting, an SOE is a wholly or majority government-owned company engaged in extractive activities on behalf of the government. Based on this, the MSGs are encouraged to discuss and document their definition of SOEs, taking national laws and government structures into account. b) Disclosures from the government and SOE(s) of their level of ownership in mining, oil, and gas companies operating within the country’s oil, gas, and mining sector, including those held by SOE subsidiaries and joint ventures and any changes in the level of ownership during the reporting period. This information should include details regarding the terms attached to their equity stake, including their responsibility to cover expenses at various phases of the project cycle, e.g., full-paid equity, free equity, and carried interest. Where there have been government and SOE(s) ownership level changes during the EITI reporting period, the government and SOE(s) are expected to disclose the transaction terms, including details regarding valuation and revenues. Where the government and SOE(s) have provided loans or loan guarantees to mining, oil, and gas companies operating within the country, details on these transactions should be disclosed | In November 2023, the MSG approved the Terms of Reference for the recruitment of a consultant to implement the BO Roadmap. Two important outputs of the roadmap are BO definition and threshold for disclosure. In the first quarter of 2024, the MNR recruited the consultant with work commencing soon thereafter to implement the BO Roadmap. independent consultants Diane Barker (from Guyana), Michael Barron and Tim Law (both from the United Kingdom) supported the Guyana Extractive Industries Transparency Initiative (GYEITI) in meeting the Beneficial Ownership transparency requirements of the EITI Standard. The project included: - The preparation of an inception report - Conducting workshops for companies, civil society organizations and government agencies - Developing a Beneficial Ownership reporting template - Collecting Beneficial Ownership data, and the production of a Beneficial Ownership register. The consultants’ report captures nine (9) key observations and offers seventeen recommendations to enhance Beneficial Ownership transparency in the extractive sector. |
| Requirement 3 Exploration and Production Requirement (3.1) Exploration. Implementing countries should disclose an overview of the extractive industries, including any significant exploration activities. 3.2 Production. Implementing countries must disclose production data for the fiscal year covered by the EITI Report, including total production volumes, the value of production by commodity, and, when relevant, state/region. This could include sources of the production data and information on how the production volumes and values disclosed in the EITI Report have been calculated. 3.3 Exports. Implementing countries must disclose export data for the fiscal year covered by the EITI Report, including total export volumes, the value of exports by commodity, and, when relevant, by state/region of origin. This could include sources of the export data and information on how the export volumes and values disclosed in the EITI Report have been calculated. |  |
| Requirement 4 Revenue Collection 4.1 Comprehensive disclosure of taxes and revenues. a) In advance of the reporting process, the multi-stakeholder group is required to agree on which payments and revenues are material. It, therefore, must be disclosed, including appropriate materiality definitions and thresholds. Payments and revenues are considered material if their omission or misstatement could significantly affect the comprehensiveness of the EITI Report. A description of each revenue stream, related materiality definitions, and thresholds should be disclosed. In establishing materiality definitions and thresholds, the multi-stakeholder group should consider the size of the revenue streams relative to total revenues. The multi-stakeholder group should document the options and rationale for establishing the definitions and thresholds. b) The following revenue streams should be included: i. The host government’s production entitlement (such as profit oil) ii. National state-owned company production entitlement iii. Profits taxes iv. Royalties v. Dividends vi. Bonuses, such as signature, discovery, and production bonuses vii. License fees, rental fees, entry fees, and other considerations for licenses and/or concessions viii. Any other significant payments and material benefit to the government. Any revenue streams or benefits should only be excluded where they are not applicable or where the multi-stakeholder group agrees that their omission will not materially affect the comprehensiveness of the EITI Report. c) Implementing countries must comprehensively reconcile government revenues and company payments under the agreed scope, including payments to and from state-owned enterprises. All companies making material payments to the government must comprehensively disclose these payments under the agreed scope. An entity should only be exempted from reporting if it can be demonstrated that its payments and revenues are not material. All government entities receiving material revenues must comprehensively disclose these revenues according to the agreed scope. d) Unless there are significant practical barriers, the government is additionally required to provide aggregate information about the total revenues received from each benefit stream agreed in the scope of the EITI Report, including payments that fall below-agreed materiality thresholds. The Independent Administrator should draw on relevant data and estimates from other sources to comprehensively account for the total government revenues where this data is unavailable. 4.2 Sale of the state’s share of production or other revenues collected in-kind. Where the sale of the state’s share of production or other revenues collected in-kind is material, the government, including state-owned enterprises, is required to disclose the volumes sold and revenues received. The published data must be disaggregated by individual buying companies and commensurate with other payments and revenue streams (Requirement 4.7.). Reporting could also break down disclosures by product type, price, market, and sale volume. Where practically feasible, the multi-stakeholder group is encouraged to task the Independent Administrator with reconciling the volumes sold and revenues received by including the buying companies in the reporting process. 4.3 Infrastructure provisions and barter arrangements. The multi-stakeholder group and the Independent Administrator are required to consider whether there are any agreements or sets of agreements involving the provision of goods and services (including loans, grants, and infrastructure works) in full or partial exchange for oil, gas, or mining exploration or production concessions or physical delivery of such commodities. To be able to do so, the multi-stakeholder group and the Independent Administrator need to gain a full understanding of the terms of the relevant agreements and contracts, the parties involved, the resources which the state has pledged, the value of the balancing benefit stream (e.g., infrastructure works), and the materiality of these agreements relative to conventional contracts. The multi-stakeholder group concludes that these agreements are material. The multi-stakeholder group and the Independent Administrator are required to ensure that the EITI Report addresses these agreements, providing a level of detail and transparency commensurate with the disclosure and reconciliation of other payments and revenue streams. Where reconciliation of key transactions is not feasible, the multi-stakeholder group should agree on an approach for unilateral disclosure by the parties to the agreement(s) to be included in the EITI Report. 4.4 Transportation revenues. Where revenues from the transportation of oil, gas, and minerals are material, the government and state-owned enterprises (SOEs) are expected to disclose the revenues received. The published data must be disaggregated to levels commensurate with other payments and revenue streams (Requirement 4.7.). Implementing countries could disclose i. A description of the transportation arrangements, including the product, transportation route(s), and the relevant companies and government entities involved in transportation, including SOE(s). ii. Definitions of the relevant transportation taxes, tariffs, or other relevant payments and the methodologies used to calculate them. iii. Disclosure of tariff rates and volume of the transported commodities. iv. Disclosure of revenues received by government entities and SOE(s) concerning oil, gas, and minerals transportation. v. Where practicable, the multi-stakeholder group is encouraged to task the Independent Administrator with reconciling material payments and revenues associated with oil, gas, and minerals transportation. 4.5 Transactions related to State-owned enterprises (SOEs). The multi-stakeholder group must ensure that the reporting process comprehensively addresses the role of SOEs, including material payments to SOEs from oil, gas, and mining companies and transfers between SOEs and other government agencies. 4.6 Sub-national payments. It is required that the multi-stakeholder group establish whether direct payments, within the scope of the agreed benefit streams, from companies to subnational government entities are material. Where material, the multi-stakeholder group is required to ensure that company payments to subnational government entities and the receipt are disclosed and reconciled in the EITI Report. 4.7 Level of disaggregation. The multi-stakeholder group is required to agree on the disaggregation level for the data publication. It is required that individual companies, government entities, and revenue streams present EITI data. Reporting at the project level is required, provided it is consistent with the United States Securities and Exchange Commission rules and the future European Union requirements. 4.8 Data timeliness. a) Implementing countries must produce their first EITI Report within 18 months of being admitted as an EITI Candidate. After that, implementing countries are expected to produce EITI Reports annually. b) Implementing countries must disclose data no older than the second to last complete accounting period, e.g., an EITI Report published in the calendar/the financial year 2016 must be based on data no later than the calendar/financial year 2014. Multi-stakeholder groups are encouraged to explore opportunities to disclose data as soon as possible, for example, through continuous online disclosures or, where available, by publishing additional, more recent contextual EITI data than the accounting period covered by the EITI revenue data. If EITI reporting is significantly delayed, the multi-stakeholder group should take steps to ensure that EITI Reports are issued for the intervening reporting periods so that every year is subject to reporting. c) The multi-stakeholder group is required to agree to the accounting period covered by the EITI Report. 4.9 Data quality and assurance. a) The EITI requires assessing whether the payments and revenues are subject to credible, independent audit, applying international auditing standards. b) It is required that payments and revenues be reconciled by a credible, independent administrator, applying international auditing standards and the administrator’s opinion regarding that reconciliation, including discrepancies, should any be identified. i. The reconciliation of company payments and government revenues must be undertaken by an Independent Administrator applying international professional standards. ii. The multi-stakeholder group must perceive the Independent Administrator as credible, trustworthy, and technically competent. The multi-stakeholder group should endorse the appointment of the Independent Administrator. iii. The multi-stakeholder group and the Independent Administrator must agree to the Terms of Reference for the EITI Report based on the standard Terms of Reference and the ‘agreed-upon procedure for EITI Reports’3 endorsed by the EITI Board. Should the multi-stakeholder group wish to adapt or deviate from these agreed-upon procedures, approval from the EITI Board must be sought in advance (Requirement 8.1). c) Where the assessment in 4.9(a) concludes that there is (i) routine disclosure of the data required by the EITI Standard in requisite detail, and (ii) that the financial data is subject to credible, independent audit, applying international standards, the multi-stakeholder group may seek Board approval to mainstream EITI implementation under the ‘Agreed upon procedure for mainstreamed disclosures.’4 Without such prior approval, adherence to 4.9.b is required. | In December 2024, the MSG of the GYEITI completed the FY 2022 EITI report. For this report, the IA, BDO/Hart Group, was hired through a competitive bidding process, administered by NPTAB of Guyana. To comply with EITI Requirements 4.3;4.4;4.6;4.9 and 5.2 b the MSG agreed upon a procedure to address data quality and assurance of information submitted by the reporting entities. To ensure the credibility of the data submitted, with the instructions and approval of the MSG the IA set the following: - The declarations made by companies and govt agencies are required to be signed by an authorized senior official (at management level) and an authorized senior official at a higher / executive level. - The declarations made by Government Agencies are required to be certified by the Auditor General that the transactions reported in the Reporting Templates are complete, and are in agreement with the government accounts for the period under review. - The Auditor General in keeping with international standards and practice certified the reporting templates provided by Government Agencies. - Extractive entities selected in the reconciliation scope were required to submit their audited financial statements. The templates for the 2022 report were approved on August 5, 2024. On June…2024, the IA held workshops with Government and Industry reporting entities on the data reporting templates which they had developed for the FY2022 report. The 2022 report was published on December 20, 2024 in keeping with the EITI Standard. The IA and MSG, with the support of the national secretariat, sought to ensure that the 2022 report go further in achieving the EITI requirements than previous reports. The multi-stakeholder group decided upon an agreed upon procedure which will be utilized for the certificate. Nation of data from state agencies. The agreed upon procedure also speaks to the Auditor General issuing an audit assurance certification for the data submitted by state agencies. |
| 5.1 Distribution of extractive industry revenues. Implementing countries must disclose a description of the distribution of revenues from the extractive industries. a) Implementing countries should indicate which extractive industry revenues are recorded in the national budget, whether cash or in-kind. Where revenues are not recorded in the national budget, the allocation of these revenues must be explained, with links provided to relevant financial reports as applicable, e.g., sovereign wealth and development funds, sub-national governments, state-owned enterprises, and other extra-budgetary entities. b) Multi-stakeholder groups are encouraged to reference national revenue classification systems and international standards such as the IMF Government Finance Statistics Manual. 5.2 Subnational transfers. a) Where transfers between national and sub-national government entities are related to revenues generated by the extractive industries and are mandated by a national constitution, statute, or other revenue-sharing mechanisms, the multi-stakeholder group is required to ensure that material transfers are disclosed. Implementing countries should disclose the revenue-sharing formula and any discrepancies between the transfer amount calculated under the relevant revenue-sharing formula and the actual amount transferred between the central government and each relevant subnational entity. The multi-stakeholder group is encouraged to reconcile these transfers. Where there are constitutional or significant practical barriers to the participation of sub-national government entities, the multi-stakeholder group may seek adapted implementation under Requirement 8.1. b) The multi-stakeholder group is encouraged to ensure that any material discretionary or ad-hoc transfers are disclosed and reconciled where possible. 5.3 Revenue management and expenditures. The multi-stakeholder group is encouraged to disclose further information on revenue management and expenditures, including a) A description of any extractive revenues earmarked for specific programs or geographic regions. This should include a description of the methods for ensuring accountability and efficiency. b) A description of the country’s budget and audit processes and links to the publicly available information on budgeting, expenditures, and audit reports. c) Timely information from the government that will further public understanding and debate around revenue sustainability and resource dependence issues. This may include the assumptions underpinning forthcoming years in the budget cycle and relating to projected production, commodity prices, revenue forecasts arising from the extractive industries, and the proportion of future fiscal revenues expected from the extractive sector. |  |
| 6.1 Social expenditures by extractive companies. a) Where material social expenditures by companies are mandated by law or the contract with the government that governs the extractive investment, implementing countries must disclose and, where possible, reconcile these transactions. Where such benefits are provided in-kind, it is required that implementing countries disclose the nature and the deemed value of the in-kind transaction. Where the beneficiary of the mandated social expenditure is a third party, i.e., not a government agency, it is required that the name and function of the beneficiary be disclosed. Where reconciliation is not feasible, countries should provide unilateral company and/or government disclosures of these transactions. b) Where the multi-stakeholder group agrees that discretionary social expenditures and transfers are material, the multi-stakeholder group is encouraged to develop a reporting process to achieve transparency commensurate with the disclosure of other payments and revenue streams to government entities. Where reconciliation of key transactions is impossible, e.g., company payments are in-kind, or to a non-governmental third party, the multi-stakeholder group may wish to agree on an approach for the voluntary unilateral company and/or government disclosures. 6.2 Quasi-fiscal expenditures. Where state participation in the extractive industries gives rise to material revenue payments, implementing countries must include disclosures from SOE(s) on their quasi-fiscal expenditures. Quasi-fiscal expenditures include arrangements whereby SOE(s) undertake public social expenditures such as payments for social services, public infrastructure, fuel subsidies, national debt servicing, etc., outside of the national budgetary process. The multi-stakeholder group must develop a reporting process to achieve transparency commensurate with other payments and revenue streams, including SOE subsidiaries and joint ventures. 6.3 The contribution of the extractive sector to the economy. Implementing countries must disclose, when available, information about the contribution of the extractive industries to the economy for the fiscal year covered by the EITI Report. It is required that this information includes the following: a) The size of the extractive industries in absolute terms and as a percentage of GDP and an estimate of informal sector activity, including but not necessarily limited to artisanal and small-scale mining. b) Total government revenues generated by the extractive industries (including taxes, royalties, bonuses, fees, and other payments) in absolute terms and as a percentage of total government revenues. c) Exports from the extractive industries in absolute terms and as a percentage of total exports. d) Employment in the extractive industries in absolute terms and as a percentage of the total employment. e) Key regions/areas where production is concentrated. | Regarding this requirement, the report talks about the contribution to the economy of the extractive sector for the year covered by the report. In addition, the Secretariat prepares a comparative study and a data dissemination bulletin covering the year of the report that speaks to the required information being disseminated. |
| 7.1 Public debate. The multi-stakeholder group must ensure that the EITI Report is comprehensible, actively promoted, publicly accessible, and contributes to public debate. Key audiences should include government, parliamentarians, civil society, companies, and the media. The multi-stakeholder group must: a) Produce paper copies of the EITI Report and ensure that they are widely distributed. The report contains extensive data, e.g., voluminous files, so the multi-stakeholder group is encouraged to make this available online. b) Agree on a clear policy on accessing, releasing, and re-using EITI data. Implementing countries are encouraged to publish EITI under an open license and inform users that information can be reused without prior consent. c) Make the EITI Report available online in an open data format (xlsx or csv) and publicize its availability. d) Ensure that the EITI Report is comprehensible, including writing in a clear, accessible style and inappropriate language. e) Ensure that outreach events are organized by the government, civil society, or companies to spread awareness of and facilitate dialogue about the EITI Report across the country. 7.2 Data accessibility. The multi-stakeholder group is encouraged to make EITI Reports machine-readable and code or tag EITI Reports and data files to compare the information with other publicly available data by adopting Board-approved EITI data standards. As per Requirement 5.1(b), the multi-stakeholder group is encouraged to reference national revenue classification systems and international standards such as the IMF Government Finance Statistics Manual. The multi-stakeholder group is encouraged to a) Produce summary reports with clear and balanced analysis of the information, ensuring that the authorship of different elements of the EITI Report is clearly stated. b) Summarize and compare the share of each revenue stream to the total amount of revenue that accrues to each respective level of government. c) Where legally and technically feasible, continuously consider automated online disclosure of extractive revenues and payments by governments and companies. This may include cases where extractive revenue data is already published regularly by the government or where national taxation systems are trending towards online tax assessments and payments. Such continuous government reporting could be considered interim reporting and an integral feature of the national EITI process, captured by the annual reconciled EITI Report. d) Undertake capacity-building efforts, especially with civil society and through civil society organizations, to increase awareness of the process, improve understanding of the information and data from the reports, and encourage the use of the information by citizens, the media, and others. 7.3 Discrepancies and recommendations from EITI Reports. To strengthen the impact of EITI implementation on natural resource governance, as per Requirement 7.4, the multi-stakeholder group is required to take steps to act upon lessons learned; to identify, investigate and address the causes of any discrepancies; and to consider the recommendations resulting from EITI reporting. 7.4 Review the outcomes and impact of EITI implementation. The multi-stakeholder group is required to review the outcomes and impact of EITI implementation on natural resource governance. a) The multi-stakeholder group is required to publish annual progress reports.5 The annual progress reports must include i. A summary of EITI activities undertaken in the previous year. | For 2024 - University of Guyana Academic Board meeting on March 12, 2024. During this online event, the Secretariat and members of the MSG had the opportunity to engage senior members of the university’s faculty on transparency within the extractive sectors. The roles of the MSG and National Secretariat were explained and as well as the aims and objectives of the EITI Standard in promoting extractive sector transparency. - University of Guyana Student Engagement on July 16, 2024 – The National Secretariat and members of the Multi Stakeholder Group organized a session with students of the University of Guyana, during which EITI was explained in detail. In addition, the presenters explained the role of the Ministry of Natural Resources, the role of the MSG and the role of Civil Society and agencies in implementing the principles of EITI. The presentation also explained how EITI came about in Guyana. The Secretariat gave a brief history of EITI in Guyana. Following the presentations, there was a question-and-answer session which had vibrant participation. - On June 29th, the Communications Officer travelled to Lethem Region 9 to conduct preparations for a community engagement with the people of Region 9. During this visit He met with a number of key stakeholders from Region 9, including the Mayor of Lethem, the Chairman of the Regional Democratic Council of Region 9, officials from the Rupununi Chamber of Commerce and Industry, and a number of other key officials. During the meeting, which lasted about one hour, the communications officer shared information regarding Guyana’s journey towards EITI implementation and some of the challenges and opportunities that it presented. Following the end of the session which included question and answers, a number of copies of our country reports were presented to each of the stakeholders present at the meeting. - On June 28 2024, the Secretariat hosted an engagement and awareness session for youths who are part of the Ministry of Natural Resources, Youth in Natural Resources Apprenticeship Program. The session shared the origins of EITI and its role in Guyana’s management of natural resources. Following the presentations, there was an opportunity for questions and answers, and the youths engaged in a fun and interactive fact-finding exercise during which they were able to share their thoughts regarding what they learned. - We have completed the Merundoi radio serial drama, which began airing in December 2024.. The project will see the airing of many episodes going into 2025. In addition to this, we intend to engage the Merundoi team for our community outreach programs. - We have successfully completed the publishing of two EITI newsletters, which covered a range of articles highlighting achievements coming out of the work plan implementation efforts. Publish newsletters are available on the GYEITI website. - The Secretariat's part in the Human Rights and Anti-Corruption Expo, held on December 9-10,2024, focused on promoting transparency and human rights. It featured interactive booths, games, and a human rights pledge wall, engaging over 100 attendees with educational materials. Despite minor challenges, the event successfully highlighted the connection between combating corruption and safeguarding rights. |

# Strengths and Weaknesses Identified in EITI Process GYEITI

Strengths

The Government of Guyana supports implementation through funding and budget support. Public statements and actions from the Head of State and at the Ministerial level demonstrate the political will to implement the EITI. While MSG attendance at meetings could be improved, the MSG is robust and provides full guidance over implementation.

Weaknesses

Privacy concerns and regulatory restrictions continue to undermine EITI disclosures. EITI awareness is low nationwide, and public debate using EITI disclosures could be strengthened. Technical training and skills development could enhance the capacity of the National Secretariat.

Opportunity

Embedding EITI disclosure requirements into sector legislation or crafting legislation to ensure reporting entities submit information in keeping with EITI requirements is critical to improving transparency in Guyana.

# Total Implementation Cost

The Government underwrites EITI implementation in Guyana through budgetary allocation to the Ministry of Natural Resources. The allocation covers staff compensation, office supplies and space, vehicle, MSG operations, outreach and dissemination, and consultancy fees for EITI reports.

Total implementation cost for 2024 was GYD161,790,258.

# Expense Report

Below is a summary of implementation expenses for FY 2024.

# Details of the MSG during the Period

GYEITI MSG comprised twelve primary members and twelve alternate members. The MSG is made up of equal representation from the government, industry, and civil society.

Below is an overview of the attendance of the MSG members at meetings:

MULTI-STAKEHOLDER GROUP STATUTORY MEETINGS HELD FROM JANUARY TO DECEMBER 2024 – 71st TO 78TH MEETINGS

Summary of attendance of MSG and Secretariat

|  | Name & Sector | Gender | Members Present | Members Absent | Alternate | Gender | Present | Absent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INDUSTRY |  |  |  |  |  |  |  |  |
| 1 | W Thompson | M | X (8) | (0) | A Gohil | M | X (2) | w/e (6) |
| 2 | R Ramjit | M | X (8) | (0) | J Vogt | M | X (7) | w/e (1) |
| 3 | A Alphonso | M | (0) | (8) | A Jagnandan | M | X (3) | w/e (5) |
| 4 | R Khan | M | X (8) | (0) | N McLean | M | (0) | (8) |
| CIVIL SOCIETY |  |  |  |  |  |  |  |  |
| 5 | D Desouza | F | X (7) | (1) | M McCormack | M | X (5) | w/e (3) |
| 6 | L Fiedtkou | F | X (8) | (0) | B Clenkian | F | X (7) | w/e (1) |
| 7 | V Radzik | F | X (8) | (0) | G Singh | M | X (5) | w/e (3) |
| 8 | K Cort-Kansinally | F | X (3) | (5) | M Williams | M | X (4) | w/e (4) |
| GOVERNMENT |  |  |  |  |  |  |  |  |
| 9 | S Roopnauth | F | X (6) | w/e (2) | T Balgobin | M | (0) | (8) |
| 10 | H Khan | F | X (5) | w/e (3) | S Richmond | M | X (5) | w/e (3) |
| 11 | V Harris | F | x (3) | w/e (5) Resigned in June, 2024 | S Hussain | M | X (5) | w/e (3) |
| 12 | M Munroe | M | x (6) | w/e (2) | M Pertab | M | X (4) | w/e (4) |

| Secretariat Staff |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | P Misir | M | X (7) | w/e (1) |  |  |  |  |
| 2 | J Earle | M | X (8) | (0) |  |  |  |  |
| 3 | R Jagarnauth | F | X (7) | w/e (1) |  |  |  |  |
| 4 | R Ramgobin | M | X (8) | (0) |  |  |  |  |
| 5 | R. Budhu | M | X (8) | (0) |  |  |  |  |