## Sheet1
GUYANA EXTRACTIVE INUDSTRIES TRANSPARENCY INITIATIVE – 3RD WORK PLAN JANUARY 2021 – DECEMBER 2022
GENERAL OBJECTIVE: Provide accurate, contextualized and useful information to promote transparency, accountability and dialogue on extractives and inform the governance of natural resources for the benefit of Guyana’s sustainable development
Specific objectives | Expected Outputs | Activities | Description | Responsible Party | By When | Indicative Cost (USD) | Funding Source | Status | Comment
Compile accurate information that is consistent with the overall objective of GYEITI | 1.1 The scope, level of materiality and reporting period have been determined | 1.1.a Gather and compile key information to help determine scope, materiality and reporting period for 3rd GYEITI Report | 2019 data on revenues, payment, reporting agencies and legal framework | National Secretariat/ MSG/Independent Administrator | 2021 Q2 | NA | GoG
|  | 1.1b Conduct at least four virtual meetings with MSG working group to discuss and determine the level of materiality, and reporting period for the 3rd Report |  | National Secretariat/MSG | 2021 Q2 | 100 | GoG
|  | 1.2a Capacity building and training programs through webinars and online seminars for National Secretariat to effectively support the MSG and GYEITI Implementation process | This includes on the job training, participation in international/regional EITI Events, exchange with Secretariats of other EITI countries | National Secretariat/**PADF and other Partner(s) | 2021 Q1-Q4 – 2022 Q1-Q4 | 50000 | GoG/Donors
|  | 1.2.b Manage and operate the GYEITI Secretariat | This includes operational costs as well as office equipment and facilities such as laptops and internet services | National Secretariat/GoG | 2021 Q1-Q4 2022 Q1-Q4 | (after budget is passed info will be provided) | GOG
|  | 1.2.c.National Secretariat will continue to organize monthly MSG meetings, conference, workshops and events through webinars and zoom meetings | All statutory meetings, conferences, workshops and other events for the MSG will be organized by the Secretariat. | National Secretariat | 2021 Q1-Q4 2022 Q1-Q4 | 10000 | GoG
| 1.3 MSG capacity on EITI has been enhanced | 1.3.a Organize information exchange events seminars/webinars between the MSGs successfully implementing the EITI | Participate in regional and international EITI Webinars. | National Secretariat, GoG | 2021 Q1-Q4 | 10000 | Donors, GoG
|  | 1.3.b. Capacity building for MSG on EITI and EITI implementation process | Training in person or virtual of MSG | MSG and National Secretariat | 2021 Q2 | 5000 | Donors-TBD Meetings to be scheduled
| 1.4 A mechanism has been established for funding of EITI Process implementation | 1.4.a Determine/confirm budget allocation by the Government of Guyana | The budgetary allocation for EITI in budget 2021 will be confirmed | GoG | 2021 Q1 | 0
|  | 1.4.b Create a funding strategy | Identify potential donors, prepare funding strategy, prepare and submit proposal to donors: WB, IDB, CDB, GIZ, etc.) | National Secretariat/MSG | 2021 Q1 | 0 | Work in progress, Meeting to be arranged with potential donors.
| 1.5. Legal, Regulatory and Institutional frameworks for EITI Reporting are in place | 1.5 a Review legal, regulatory and institutional framework to identify potential obstacles to GYEITI implementation | Special attention should be paid to revision of legal and regulatory frameworks for confidentiality of information, disclosure of beneficial ownership information as well as options for special agreements to ensure disclosure of information needed for the EITI Report | Consultant/GoG | 2021 Q2-Q4 | TBD | GoG/Donors
|  | 1.5.b Conduct at least two virtual meetings with relevant stakeholders within the oil and gas sector on legal reform in Oil and Gas | To conduct legislative reform | GoG/NS | Ongoing | 100 | NA
|  | 1.5.c Review the organizational structure of GGMC | The organizational chart for GGMC will be reviewed and recommendations made for improvement | GGMC | Completed. Report on the restructuring will be requested from MNR | NA | NA
|  | 1.5.d Formally and informally engage stakeholders operating in the extractive sector through round table meetings or virtual meetings with a view to encourage greater participation in the EITI Process. | Miners and other sectors will be encouraged to participate in the EITI process | Secretariat/MSG/MNR | Ongoing | 5000 | GoG
|  | 1.5.e Establish a register of reporting entities. | A register will be established for reporting entities | Secretariat/MSG | 2021 Q1-Q2 | NA | NA
|  | 1.5.f Monitor submission timelines and any foreseeable deviations. | A register will be established for reporting entities | Secretariat/MSG | 2022 Q1-Q2 | NA | NA
|  | 1.5.g. Review existing revenue collection system and make recommendations to government to implement a unique identification numbering system for all government agencies. |  | IA | 2021 Q 1-Q2 | NA | NA
|  | 1.5.h Conduct a review of all relevant existing Legislations and identify and document areas related to confidentiality issues |  | Consultant | 2021 Q1-Q4 | NA | NA
|  | 1.5.i Formulate and submit recommendations to remove any existing restrictions which hinders the full satisfaction of the EITI 2019 Standard. |  | IA | 2021 Q2 | NA | NA
CONTRACT TRANSPARENCY
|  | 1.6.a Conduct at least one meeting with government agencies to discuss their contracts, licenses, environmental permits, environmental impact assessment disclosure policy that govern the exploration and exploitation of oil, gas and minerals | To satisfy the EITI Requirement 2.4 on disclosure of all oil gas and mineral agreements and licenses that are granted, entered into or amended from 1 January 2020 | Secretariat/MSG/MNR | 2021 Q1-Q4 2022 Q1-Q4 | 2000 | GoG/Donors
|  | 1.6.b MSG will form a subcommittee that will determine a strategy for disclosure of all contracts, licenses, environmental permits and environmental impact assessment entered into, signed or amended from January 1, 2021and present recommendations to MSG approval (the contract disclosure strategy/plan will include clear time frame for implementation, addressing any barriers to comprehensive disclosure). |  | MSG/Secretariat | 2021Q2-Q3 | NA | NA
|  | 1.6.c Secretariat will draft a contract disclosure paper capturing the current approach to licenses, contracts, environmental permits and Environmental impact assessment by various government agencies and any gaps in disclosure for discussion at MSG. |  | MSG/Secretariat | 2021Q2-Q4 | NA | NA
|  | 1.6.d Present MSG plan on contract disclosure to EITI Champion for government's consideration |  | MSG/Secretariat | 2021Q2-Q5 | NA | NA
|  | 1.6.e Get the support of the Government to have the policy on contract disclosure publicly codified. |  | MSG/Secretariat | 2021Q2-Q6 | NA | NA
LICENSE REGISTER
|  | 1.7.a. Conduct at least three virtual meetings with relevant stakeholders to discuss their existing licensing procedures and determine the format for a publicly accessible register of all licenses for the exploration of oil, gas and minerals. | To establish a license, Register of all licenses for the exploration of oil, gas and minerals | Secretariat/MSG | 2021 Q1- Q2 | 1000 | GoG
SYSTEMATIC DISCLOSURE
|  | 1.8.a Review legislation to determine legal and institutional framework for public disclosure of information. |  | Consultant | 2021 Q3, Q4 | 10000 | Donors
1.8.b Conduct scoping study on systematic disclosure.
1.8.c.Formulate conclusion and recommendation for Public Disclosure
|  | 1.8.d Identify options for appropriate hardware and software that can be used by reporting entities. (b) Conduct a workshop to build capacity – recruit and train staff on the use of the software, data collection, analysis and report compilation. |  | Consultant | 2021 Q3, Q4 | 3000 | GOG/Donors
PREPARATION AND CREATION OF BENEFICIAL OWNERSHIP REGISTER
|  | 1.9.a Conduct legal scoping and identify potential obstacles to implementation of beneficial owners Register in keeping with the recommendations from the IA | Determine legal scope and define beneficial ownership, stakeholder threshold and politically exposed persons (PEPs) | MSG/Secretariat/IA | 2021 Q1 -Q3 | 15000 | Donors-TBD
|  | 1.9.b. Propose approach to systemized and publish information on BO | Discuss strategy for creating templates and gathering details for initial draft register of beneficial ownership | MSG/Secretariat/IA | 2022 Q1 -Q3 | 15001 | Donors-TBD
|  | 1.9.c Propose an approach to systemized and publish information on Beneficial ownership ( (d) to publish BO Registry on GYEITI official website. |  | MSG/National Secretariat/Consultant | 2021Q2 | 5000 | Donors-TBD
|  | 1.9.e MSG and Secretariat to engage and participate in webinars, in partnerships and sharing experiences on beneficial ownership and related topics |  | National Secretariat/MSG | 2021Q2 | 2000 | GoG
| 10.Studies have been conducted to enhance the scope of work for 2nd and 3rd Reports relevant to beneficial ownership disclosure by 01.01.2020 | 10.a Request for companies to disclose Beneficial ownership information for inclusion in the EITI Report | Conduct symposium with external assistance on Beneficial Ownership (EITI International Secretariat and other countries with relevant experience) | National Secretariat/MNR | Ongoing | 5000 | GoG
|  |  | i. Agree definition, threshold, templates | National Secretariat | Ongoing | 5000 | GoG/Donors
ii. Consider data collection procedures (timeliness, reporting mechanism, hosting agency, data security, etc.)
iii. Define data quality/assurances
iv. Pilot data collection/registry
v. Lessons learned
vi. Establish disclosure protocol to be used for BO disclosure (to implement as required by 01.01.2020)
| 11.Studies have been conducted to enhance the scope for future GYEITI reports | 11.a.Design and implement studies to formulate recommendations to enhance the scope of future GYEITI reports. | Study on the characteristics of the artisanal and small-scale mining sector and/or quarrying and if/how to include it in EITI reporting | National Secretariat/MSG/ Consultant(s) | 2021 Q3 | 15000 | Donors
|  |  | Study on the characteristics of the forestry sector and if/how to include it in EITI Report |  | 2021 Q3
|  |  | Study on company expenditures related to social/community projects and corporate social responsibility projects and if/how to include it in EITI Reporting. |  | 2021 Q3
Implementation of Recommendation for 1st Report
| 12.MSG will determine the definition for project | 12.a.MSG to determine definition project = “Operational activities that are governed by a single contract, license, lease, concession or similar legal agreement, and form the basis for payment liabilities with government” | Definition for project will be made by MSG | MSG/Consultant | 2021 Q1-Q2 | NA | NA
|  | 12.b.Engage as far as practicable reporting entities for government and companies to review and document existing government data collection systems to determine whether the system adequately disaggregate payment flows, production and export by projects and by license, including TIN numbers and beneficial ownership details and project level reporting. |  | Secretariat/Consultant | 2021 Q2-Q3 | 40000 | Donors
|  | 12.c.To conduct a study and make recommendations to support the efforts of reporting entities to establish and use a unified system for information and data collection at project level |  | Consultant/Secretariat | 2021 Q3-Q4 | 100000 | Donors-TBD
|  | 12.d.Ensure Independent Administrator(IA) conducts assessment of data collection system in government agencies, identify weaknesses and make recommendations for improvements to allow for accurate documentation of data on exploration, production and export. Conduct at least three meetings with relevant reporting entities to review and document existing system to determine: (a( whether provision is made for an automated data verification and control system that can ensure uniformity of export data reported to GGMC and GGB by mining entities and execute simple analysis for data consistency purposes. (b) To determine collection mechanisms and recommend a common industry wide computerized system which can eliminate avoidable data variations and that government agencies perform monthly data review and control to alleviate discrepancies in production and export volume and value. |  | Secretariat/Consultant
|  | 12.e.Produce summary of the findings and recommendations from the GYEITI 1st and 2nd Reports and an overview of the issues to be focused in the 3rd Report |  | Consultant | 2021 Q3 | NA | NA
Communications and Outreach
Disseminate widely the information obtained under the EITI Standard to promote stakeholder dialogue | 13.Communications scoping study and outreach strategy has been designed | 13.a.Contracting of consulting firm to design a communications and outreach strategy |  | Consultant | 2021 Q1-Q4 | 10000 | Donors
|  | 13.b.Produce a strategic public relations ad, app, community radio programs and video for mass sensitization |  | Consultant
|  | 13.c.Design and create GYEITI banners, promotional materials and items to distribute during defined public outreach activities | Translators are expected to be present at key public outreach activities if/when audience so requires | Consultant
| 14. A communications and outreach strategy has been implemented | 14.a.Design, publish and regularly update GYEITI website and production of GYEITI information materials |  | Secretariat/MSG | 2021 Q1-Q4 2022Q1-Q4 | 110000 | GoG/Donors
|  | 14.b.Draft/design easily accessible (basic) versions of the GYEITI Reconciliation Report and the Validation Report | Basic reports are expected to be made available in English | Consultant | 2021 Q2
|  | 14.c.Facilitate three virtual workshops and training sessions to engage youths in GYEITI: Compose GYEITI jingle and song |  | Secretariat/Consultant | 2021 Q3
|  | 14.d.Prepare a variety of communications products, customizing the EITI Report to suit various civil society audiences, especially indigenous and hinterland communities. |  | Secretariat/Consultant | 2021 Q2, Q3
COMMUNICATION AND OUTREACH –PROMOTING CONTENT OF 1ST REPORT
| 15.Informed citizenry who can demand transparency in Government with regard to their national patrimony and a more well-informed business sector | 15.a.Activities will include social media and virtual engagement to as many stakeholders as possible | The outcome will be a better- informed citizenry who can demand transparency in Government with regard to their national patrimony and a more well-informed business sector | Secretariat | 2021 Q2-Q4 | 5000 | GoG
|  | 15.b. Publication of educational reference materials. |  | Secretariat/Consultant | 2021 Q2-Q4 | 5000 | GoG
|  | 15.c.Engage a local media content writer to do a content writing for media releases on EITI report, outcomes, launching newsletters and other media activities |  | PADF | 2021 Q3 | TBD | PADF
|  | 15.d.Activities include but not limited to publication of newsletter, press releases, media articles, social media posts, photo galleries, video jingles and informercials , Skype, Microsoft Teams and Zoom meetings and face to face engagements where possible |  | Secretariat | Ongoing | 10000 | GoG/Donors
IMPLEMENTATION OF RECOMMENDATION FOR 2ND REPORT - PENDING
| 16.Media workers have been trained to report on GYEITI and other issues of the extractive industry | 16.a.Conduct workshops and training sessions for media workers on GYEITI implementation and other issues |  | Consulting firm under supervision of National Secretariat and approval of MSG. | 2021 Q1-Q4 | 15000 | GoG/Donors
Promote timely reconciliation of the information provided under the EITI Standard | 17.Reporting templates and mechanisms have been designed and are submitted by companies and government | 17.a.Prepare TOR for the Independent Administrator for preparation of 3rd EITI Report | The TOR for the hiring of the IA will be prepared for preparation of GYEITI 3rd Report. | National Secretariat | Ongoing | NA | NA
|  | 17.bSelect and Appoint Independent Administrator | Selection of the Independent Administrator to be based on a transparent bidding process, based on a TOR approved by the MSG | MSG/National Secretariat | 2021 Q2 | 60000 |  | GoG/Donors
|  | 17.cDraft templates and data collection and reporting mechanisms |  | MSG/National Secretariat | 2021 Q2
|  | 17.d.Facilitate a series of MSG meetings to discuss and approve templates and mechanisms |  |  | 2021 Q2, Q3 | 1000
|  | 17.e.Government and companies report data, using agreed template and mechanisms |  |  | 2021 Q2, Q3
| 18.3rd Report prepared, reviewed and submitted to EITI International Secretariat | 18.a.Independent Administrator collects and analyzes data and produce draft of 3rd GYEITI Report |  |  | 2021Q2-Q4
|  | 18.b.At least three workshops to discuss, comment and approve GYEITI Report. |  |  | 2021 Q4 | 2000
|  | 18.c.Independent Administrator produces final version of 3rd GYEITI Report |  |  | 2022 Q1
|  | 18.d.MSG Reviews and submits 3RD GYEITI Report to the International EITI Secretariat |  |  | 2022 Q1
EXECUTION OF NOMINATION PROCESS FOR NEW MSG
| 19.There will be the appointment and installation of new MSG members/alternates to serve GYEITI | 19.a.Secretariat will write to the respective sector representative to inform that the tenure of current MSG will come to an end in February 2020 and request the sector caucus and submit names of their nominee for the appointment of new MSG. |  | Secretariat | Ongoing | NA | NA
|  | 19.b.Advertise in the daily newspapers the need for the nomination of MSG members/alternates from government, civil society and industry. |  | MNR | Ongoing | 1000 | GoG
|  | 19.c.Conduct and facilitate one seminar with civil society, government and industry representatives on EITI and the nomination process for MSG members/alternates |  | National Secretariat/MNR/MSG | 2021 Q1 | 5000 | GoG
|  | 19.d.Issue Letters of appointment to new MSG members/alternates |  | MNR | 2021 Q2 | NA | NA
| 20. Greater gender diversity in the MSG and greater awareness in the MSG and wider sector of the need for gender parity. | 20.a. MSG to consider gender balance in their representation in the progress towards gender parity per 2019 EITI Standard |  | MNR/MSG | 2021 Q2 | NA | NA
PREPARATION FOR 1ST EITI VALIDATION – SCHEDULED TO COMMENCE APRIL 2021
| 21.Validation will be conducted | 21.a Prior to the commencement of validation, the MSG will undertake a self-assessment of adherence to the EITI Standard | The Validation for Guyana’s 1st Report to commence | MSG/National Secretariat | 2021 Q3 | TBD | NA
|  | 21.b,Initial data collection and stakeholder consultation (a) Desk Review (detailed review of available documentation relating to the country’s compliance with EITI Standard |  | EITI International Secretariat | 2021Q3 | TBD | EITI International
|  | 21.c.Board Review Validator’s assessment of GYEITI and feedback from GYEITI MSG |  | EITI International Secretariat | 2021 Q3 | TBD | EITI International
|  | 21.d.Validator Review of GYEITI Commences |  | Independent Validator | 2021Q3 | TBD | EITI International
|  | 21.e. Validator submit findings of EITI implementation processes in Guyana |  | Independent Validator | 2021Q3 | TBD | NA